## Labor Cost Estimate
Task Number | Task Name | Resource Type | Resource Name | Team Estimate | PM Estimate | Cost of Component, Phase, or Sub Phase | PM Hours | SRD Hours | BED Hours | FED Hours | DBA Hours | QAT1Hours | ITM Hours | SM Hours | SA Hours | QAT2 Hours | JD Hours | Duration (Hours) | Duration (Days) | Hourly Rate (per task and average) | Daily Rate (per task and average)
| Pre-Development Activities |  |  |  |  | 10424 | [11 empty] | 171 | 21.375 | 60.9591 | 487.6725
| Requirements Analysis |  |  |  |  | 5304 | [11 empty] | 78 | 9.75 | 68 | 544
PDA-1 | Gather requirements from stakeholders | FTE (1) | PM | 0 | 2720 | 2720 | 40 | [10 empty] | 40 | 5 | 68 | 544
PDA-2 | Create software system requirements analysis | FTE (3) | PM, ITM, SRD | 1360 | 680 | 2040 | 10 | 10 |  |  |  |  | 10 |  |  |  |  | 30 | 3.75 | 68 | 544
PDA-3 | Receive approval of requirements analysis | FTE (1) | PM | 0 | 544 | 544 | 8 | [10 empty] | 8 | 1 | 68 | 544
| Feasibility Study |  |  | 0 | 0 | 2380 | [11 empty] | 35 | 4.375 | 68 | 544
PDA-4 | Conduct cash flow analysis | FTE (1) | PM | 0 | 1360 | 1360 | 20 | [10 empty] | 20 | 2.5 | 68 | 544
PDA-5 | Conduct risk assessment | FTE (1) | PM | 0 | 1020 | 1020 | 15 | [10 empty] | 15 | 1.875 | 68 | 544
| Development Environment Setup |  |  |  |  | 2740 | [11 empty] | 58 | 7.25 | 47.2414 | 377.931
PDA-5 | Update laptops to Windows 11 OS | FTE (9) | PM, ITM, SRD, BED, FED, DBA, QAT1, QAT 2, JD | 744 | 136 | 880 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 0 | 2 | 2 | 18 | 2.25 | 48.8889 | 391.1111
PDA-6 | Install and configure Visual Studio Code | FTE (9) | ITM, SRD, BED, FED, DBA, QAT1, QAT 2, JD | 372 | 0 | 372 |  | 1 | 1 | 1 | 1 | 1 | 1 |  | 0 | 1 | 1 | 8 | 1 | 46.5 | 372
PDA-7 | Install and configure Postman, Maven, and Junit 5 testing software | FTE (9) | ITM, SRD, BED, FED, DBA, QAT1, QAT 2, JD | 744 | 0 | 744 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 0 | 2 | 2 | 16 | 2 | 46.5 | 372
PDA-8 | Install and configure PostgreSQL and SQL interface | FTE (9) | ITM, SRD, BED, FED, DBA, QAT1, QAT 2, JD | 744 | 0 | 744 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 0 | 2 | 2 | 16 | 2 | 46.5 | 372
| Release 1: Basic (Core) System |  |  |  |  | 97340 | [11 empty] | 2018 | 252.25 | 48.2359 | 385.887
| Mock Up User Interfaces |  |  |  |  | 2397 | [11 empty] | 61 | 7.625 | 39.2951 | 314.3607
R1-1 | Mock up user interface for Medisail customers | FTE (2) | FED, JD | 501 | 0 | 501 |  |  |  | 1 | [6 empty] | 12 | 13 | 1.625 | 38.5385 | 308.3077
R1-2 | Mock up user interface for suppliers | FTE (2) | FED, JD | 501 | 0 | 501 |  |  |  | 1 | [6 empty] | 12 | 13 | 1.625 | 38.5385 | 308.3077
R1-3 | Mock up user interface for Medisail non-technical employees | FTE (2) | FED, JD | 353 | 0 | 353 |  |  |  | 1 | [6 empty] | 8 | 9 | 1.125 | 39.2222 | 313.7778
R1-4 | Mock up marketplace user interface | FTE (2) | FED, JD | 558 | 0 | 558 |  |  |  | 2 | [6 empty] | 12 | 14 | 1.75 | 39.8571 | 318.8571
R1-5 | Mock up shopping cart and checkout interfaces | FTE (2) | FED, JD | 353 | 0 | 353 |  |  |  | 1 | [6 empty] | 8 | 9 | 1.125 | 39.2222 | 313.7778
R1-6 | Mock up login portal user interface | FTE (2) | FED, JD | 131 | 0 | 131 |  |  |  | 1 | [6 empty] | 2 | 3 | 0.375 | 43.6667 | 349.3333
| Database Creation |  |  |  |  | 1632 | [11 empty] | 48 | 6 | 34 | 272
R1-7 | Create database | FTE (1) | DBA | 136 | 0 | 136 |  |  |  |  | 4 | [6 empty] | 4 | 0.5 | 34 | 272
R1-8 | Create tables with associated fields | FTE (1) | DBA | 136 | 0 | 136 |  |  |  |  | 4 | [6 empty] | 4 | 0.5 | 34 | 272
| Fill Inventory, Supplier, Distributor, and Customer Tables with Dummy Data |  |  |  |  | 1360 | [11 empty] | 40 | 5 | 34 | 272
R1-9 | Fill Medical Supplies table with dummy data | FTE (1) | DBA | 272 | 0 | 272 |  |  |  |  | 8 | [6 empty] | 8 | 1 | 34 | 272
R1-10 | Fill Medical Supplier table with dummy data | FTE (1) | DBA | 272 | 0 | 272 |  |  |  |  | 8 | [6 empty] | 8 | 1 | 34 | 272
R1-11 | Fill Distributor table with dummy data | FTE (1) | DBA | 272 | 0 | 272 |  |  |  |  | 8 | [6 empty] | 8 | 1 | 34 | 272
R1-12 | Fill Customer table with dummy data | FTE (1) | DBA | 272 | 0 | 272 |  |  |  |  | 8 | [6 empty] | 8 | 1 | 34 | 272
R1-13 | Write SQL script to designate primary and foreign keys of each table in the database | FTE(1) | DBA | 272 | 0 | 272 |  |  |  |  | 8 | [6 empty] | 8 | 1 | 34 | 272
| Create Server and API Interfaces |  |  |  |  | 3748 | [11 empty] | 82 | 10.25 | 45.7073 | 365.6585
R1-14 | Develop core functionalities of RESTful server | FTE (2) | BED, JD | 1288 | 0 | 1288 |  |  | 12 | [7 empty] | 16 | 28 | 3.5 | 46 | 368
R1-15 | Create API endpoints for user API interface | FTE (1) | BED, JD | 502 | 0 | 502 |  |  | 1 | [7 empty] | 12 | 13 | 1.625 | 38.6154 | 308.9231
R1-16 | Create API endpoints for Medisail API interface | FTE (1) | BED, JD | 502 | 0 | 502 |  |  | 1 | [7 empty] | 12 | 13 | 1.625 | 38.6154 | 308.9231
R1-17 | Write SQL script to query data from Inventory Database | FTE (1) | BED, JD | 928 | 0 | 928 |  |  | 16 | [8 empty] | 16 | 2 | 58 | 464
R1-18 | Test endpoints in Postman | FTE (1) | BED, JD | 528 | 0 | 528 |  |  | 4 | [7 empty] | 8 | 12 | 1.5 | 44 | 352
| Database Modification |  |  |  |  | 2256 | [11 empty] | 66 | 8.25 | 34.1818 | 273.4545
| Fill Inventory, Supplier, Distributor, and Customer Tables with Authentic Data |  |  |  |  | 2256 | [11 empty] | 66 | 8.25 | 34.1818 | 273.4545
R1-19 | Fill Medical Supplies table with data in fields: Inventory SKU Number (Integer), Item Name (String), Manufacturer (String), Listing Price (float), Supplier Name (String), Expiration Date (date), Generic Medicine (boolean), Brand Name Medicine (boolean) | FTE (1) | DBA | 408 | 0 | 408 |  |  |  |  | 12 | [6 empty] | 12 | 1.5 | 34 | 272
R1-20 | Fill Medical Supplier table with data in fields: Supplier ID (Integer), Supplier Name (String), Supplier Primary Address (String), Phone Number (String), Supplier Email (String), Better Business Bureau Rating (String), General Notes (String) | FTE (1) | DBA | 408 | 0 | 408 |  |  |  |  | 12 | [6 empty] | 12 | 1.5 | 34 | 272
R1-21 | Fill Distributor table with data in fields: Distributor ID (Integer), Distributor Name (String), Distributor Primary Address (String), Phone Number (String), Distributor Email (String), Better Business Bureau Rating (String), General Notes (String) | FTE (1) | DBA | 408 | 0 | 408 |  |  |  |  | 12 | [6 empty] | 12 | 1.5 | 34 | 272
R1-22 | Fill Customer table with data in fields: Customer ID (Integer), Customer Name (String), Subscription Tier (Integer), Item Purchased (String), Customer Primary Address (String), Phone Number (String), Customer Email (String), | FTE (1) | DBA | 408 | 0 | 408 |  |  |  |  | 12 | [6 empty] | 12 | 1.5 | 34 | 272
R1-23 | Revise SQL script to query authentic data | FTE (1) | DBA | 408 | 0 | 408 |  |  |  |  | 12 | [6 empty] | 12 | 1.5 | 34 | 272
R1-24 | Retest API endpoints in Postman to ensure that authentic data is correctly accessed | FTE (2) | BED, JD | 216 | 0 | 216 |  |  |  |  | 2 | [5 empty] | 4 | 6 | 0.75 | 36 | 288
| Implement User Interfaces |  |  |  |  | 10048 | [11 empty] | 224 | 28 | 44.8571 | 358.8571
R1-25 | Develop marketplace user interface | FTE (2) | FED, JD | 1800 | 0 | 1800 |  |  |  | 16 | [6 empty] | 24 | 40 | 5 | 45 | 360
R1-26 | Develop customer user interface | FTE (2) | FED, JD | 1800 | 0 | 1800 |  |  |  | 16 | [6 empty] | 24 | 40 | 5 | 45 | 360
R1-27 | Develop shopping cart and checkout interface | FTE (2) | FED, JD | 1800 | 0 | 1800 |  |  |  | 16 | [6 empty] | 24 | 40 | 5 | 45 | 360
R1-28 | Develop supplier user interface | FTE (2) | FED, JD | 1800 | 0 | 1800 |  |  |  | 16 | [6 empty] | 24 | 40 | 5 | 45 | 360
R1-29 | Develop Medisail user interface | FTE (2) | FED, JD | 1800 | 0 | 1800 |  |  |  | 16 | [6 empty] | 24 | 40 | 5 | 45 | 360
R1-30 | Develop login interface | FTE (2) | FED, JD | 1048 | 0 | 1048 |  |  |  | 8 | [6 empty] | 16 | 24 | 3 | 43.6667 | 349.3333
| Documentation |  |  |  |  | 2720 | [11 empty] | 40 | 5 | 68 | 544
R1-31 | Write documentation for core system | FTE (2) | SRD, ITM | 2720 | 0 | 2720 |  | 20 |  |  |  |  | 20 |  |  |  |  | 40 | 5 | 68 | 544
| Test Core System |  |  |  |  | 61124 | [11 empty] | 1292 | 161.5 | 47.3096 | 378.4768
| Unit Testing |  |  |  |  | 13908 | [11 empty] | 356 | 44.5 | 39.0674 | 312.5393
R1-32 | Write unit tests for server | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R1-33 | Write unit tests for Medisail API interface | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R1-34 | Write unit tests for user API interface | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R1-35 | Write tests for customer user interface | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R1-36 | Write tests for supplier user interface | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R1-37 | Write tests for Medisail user interface | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R1-38 | Write tests for marketplace interface | FTE (2) | QAT1, QAT2 | 600 | 0 | 600 | [5 empty] | 12 |  |  |  | 12 |  | 24 | 3 | 25 | 200
R1-39 | Write tests for shopping cart interface | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R1-40 | Write tests for checkout interface | FTE (2) | QAT1, QAT2 | 300 | 0 | 300 | [5 empty] | 6 |  |  |  | 6 |  | 12 | 1.5 | 25 | 200
R1-41 | Conduct back end unit tests | FTE (2) | QAT1, QAT2 | 300 | 0 | 300 | [5 empty] | 6 |  |  |  | 6 |  | 12 | 1.5 | 25 | 200
R1-42 | Conduct user interface tests | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R1-43 | Communicate results of unit tests with development team | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R1-44 | Modify system based on test results (if needed) | FTE (2) | QAT1, QAT2 | 300 | 0 | 300 | [5 empty] | 6 |  |  |  | 6 |  | 12 | 1.5 | 25 | 200
R1-45 | Retest user interfaces | FTE (4) | QAT1, QAT2, ITM, SRD | 944 | 544 | 1488 | 8 |  |  |  |  | 8 | 8 |  |  | 8 |  | 32 | 4 | 46.5 | 372
R1-46 | Reteset back end | FTE (3) | SRD, BED, FED | 7320 | 0 | 7320 |  | 40 | 40 | 40 | [7 empty] | 120 | 15 | 61 | 488
R1-47 | Retest user interfaces | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R1-48 | Reteset back end | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
| Integration Testing |  |  |  |  | 19728 | [11 empty] | 416 | 52 | 47.4231 | 379.3846
R1-49 | Write integration tests between user interfaces and server | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R1-44 | Write integration tests between server and database | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R1-45 | Write mocked integration tests between user interfaces and database | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R1-46 | Conduct integration tests between user interfaces and server | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R1-47 | Conduct integration tests between server and database | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R1-48 | Conduct integration tests between user interfaces and database | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R1-49 | Communicate results of integration tests with development team | FTE (4) | QAT1, QA2, ITM, SRD | 944 | 544 | 1488 | 8 |  |  |  |  | 8 | 8 |  |  | 8 |  | 32 | 4 | 46.5 | 372
R1-50 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 14640 | 0 | 14640 |  | 80 | 80 | 80 | [7 empty] | 240 | 30 | 61 | 488
R1-51 | Retest integration between user interface and server | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R1-52 | Retest integration between server and database | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R1-53 | Retest integration between user interface and database | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
| System Testing |  |  |  |  | 27488 | [11 empty] | 520 | 65 | 52.8615 | 422.8923
R1-54 | Write system tests of the entire core system | FTE (2) | QAT | 800 | 0 | 800 | [5 empty] | 16 |  |  |  | 16 |  | 32 | 4 | 25 | 200
R1-55 | Conduct system tests of the core system | FTE (2) | QAT, SRD, PM | 4720 | 2720 | 7440 | 40 | 40 |  |  |  | 40 |  |  |  | 40 |  | 160 | 20 | 46.5 | 372
R1-56 | Communicate results of system tests with development teams | FTE (2) | QAT, SRD, PM | 1088 | 544 | 1632 | 8 | 8 |  |  |  |  | 8 |  |  |  |  | 24 | 3 | 68 | 544
R1-57 | Modify system based on test results (if needed) | FTE (2) | SRD, BED, FED | 14640 | 0 | 14640 |  | 80 | 80 | 80 | [7 empty] | 240 | 30 | 61 | 488
R1-58 | Reconduct system tests | FTE (2) | QAT, SRD, PM | 1888 | 1088 | 2976 | 16 | 16 |  |  |  | 16 |  |  |  | 16 |  | 64 | 8 | 46.5 | 372
| Deploy Release 1 |  |  |  |  | 13415 | [11 empty] | 205 | 25.625 | 65.439 | 523.5122
| Conduct Required Trainings |  |  |  |  | 6328 | [11 empty] | 96 | 12 | 65.9167 | 527.3333
R1-60 | Train sales manager on core e-procurement system | FTE (2) | PM, SM | 2520 | 2720 | 5240 | 40 | [6 empty] | 40 |  |  |  | 80 | 10 | 65.5 | 524
R1-61 | Train Medisail non-technical employees on core e-procurement system | FTE (1) | PM | 0 | 1088 | 1088 | 16 | [10 empty] | 16 | 2 | 68 | 544
| Pre-Deployment Marketing |  |  |  |  | 2520 | [11 empty] | 40 | 5 | 63 | 504
R1-61 | Create advertisement materials for core product | FTE (1) | SM | 1008 | 0 | 1008 | [7 empty] | 16 |  |  |  | 16 | 2 | 63 | 504
R1-62 | Identify pilot customers | FTE (1) | SM | 1512 | 0 | 1512 | [7 empty] | 24 |  |  |  | 24 | 3 | 63 | 504
| Product Deployment |  |  | 0 |  | 2992 | [11 empty] | 44 | 5.5 | 68 | 544
R1-63 | Deploy core system | FTE (1) | SRD | 272 | 0 | 272 |  | 4 | [9 empty] | 4 | 0.5 | 68 | 544
R1-64 | Monitor system performance after deployment | FTE (1) | SRD | 2720 | 0 | 2720 |  | 40 | [9 empty] | 40 | 5 | 68 | 544
| Collect Customer Feedback |  |  |  |  | 1575 | [11 empty] | 25 | 3.125 | 63 | 504
R1-65 | Create customer survey | FTE (1) | SM | 252 | 0 | 252 | [7 empty] | 4 |  |  |  | 4 | 0.5 | 63 | 504
R1-66 | Send customer survey to pilot customers | FTE (1) | SM | 63 | 0 | 63 | [7 empty] | 1 |  |  |  | 1 | 0.125 | 63 | 504
R1-67 | Collect and analyze customer feedback | FTE (1) | SM | 1008 | 0 | 1008 | [7 empty] | 16 |  |  |  | 16 | 2 | 63 | 504
R1-68 | Share customer feedback with team | FTE (1) | SM | 252 | 0 | 252 | [7 empty] | 4 |  |  |  | 4 | 0.5 | 63 | 504
| Release 2: Integrated System |  |  |  |  | 72235 | [11 empty] | 1432 | 179 | 50.4434 | 403.5475
| Adjust Plan Based on Customer Feedback |  |  |  |  | 2176 | [11 empty] | 32 | 4 | 68 | 544
R2-1 | Determine which aspects of feedback are relevant | FTE (2) | PM, SRD | 544 | 544 | 1088 | 8 | 8 | [9 empty] | 16 | 2 | 68 | 544
R2-2 | Revise Release 2 requirements based on feedback assessment | FTE (2) | PM, SRD | 544 | 544 | 1088 | 8 | 8 | [9 empty] | 16 | 2 | 68 | 544
| Modify Database Functionality |  |  |  |  | 1994 | [11 empty] | 53 | 6.625 | 37.6226 | 300.9811
| Make Static Tables Dynamic |  |  |  |  | 1178 | [11 empty] | 29 | 3.625 | 40.6207 | 324.9655
R2-3 | Update endpoints in server to allow for database updates | FTE (2) | BED, JD | 824 | 0 | 824 |  |  | 4 | [7 empty] | 16 | 20 | 2.5 | 41.2 | 329.6
R2-4 | Test mock updates in database | FTE (2) | BED, JD | 354 | 0 | 354 |  |  | 1 | [7 empty] | 8 | 9 | 1.125 | 39.3333 | 314.6667
| Create Customer Statistics Table |  |  |  |  | 272 | [11 empty] | 8 | 1 | 34 | 272
R2-5 | Fill Customer Statistics table with data in fields: Customer ID (Integer), Customer Name (String), Subscription Tier (Integer), Orders per Month (Integer), Average Order Total (float), Monthly Average Order Total (float), Most Purchased Product (String) | FTE (1) | DBA | 272 | 0 | 272 |  |  |  |  | 8 | [6 empty] | 8 | 1 | 34 | 272
| Create Supplier Statistics Table |  |  |  |  | 544 | [11 empty] | 16 | 2 | 34 | 272
R2-6 | Fill Supplier Statistics table with data in fields: Supplier ID (Integer), Supplier Name (String), Products Purchased per Month (Integer), Most Purchased Product (String), Average Sales per Month (Integer) | FTE (1) | DBA | 272 | 0 | 272 |  |  |  |  | 8 | [6 empty] | 8 | 1 | 34 | 272
R2-7 | Write SQL script to designate primary and foreign keys of new tables in the database | FTE (1) | DBA | 272 | 0 | 272 |  |  |  |  | 8 | [6 empty] | 8 | 1 | 34 | 272
| Update Server and API Interfaces |  |  |  |  | 6416 | [11 empty] | 128 | 16 | 50.125 | 401
R2-8 | Create endpoints in server to allow for modification of new database tables | FTE (2) | BED, JD | 760 | 0 | 760 |  |  | 8 | [7 empty] | 8 | 16 | 2 | 47.5 | 380
R2-9 | Create endpoints in user API interface that allow suppliers to post and remove products from marketplace | FTE (2) | BED, JD | 760 | 0 | 760 |  |  | 8 | [7 empty] | 8 | 16 | 2 | 47.5 | 380
R2-10 | Create GET endpoints in Medisail API interface to access customer and supplier statistics data | FTE (2) | BED, JD | 760 | 0 | 760 |  |  | 8 | [7 empty] | 8 | 16 | 2 | 47.5 | 380
R2-11 | Develop functionality for statistics charting in Medisail API interface | FTE (2) | BED, JD | 2912 | 0 | 2912 |  |  | 40 | [7 empty] | 16 | 56 | 7 | 52 | 416
R2-12 | Test endpoints in Postman | FTE (2) | BED, JD | 1224 | 0 | 1224 |  |  | 16 | [7 empty] | 8 | 24 | 3 | 51 | 408
| Update User Interfaces |  |  |  |  | 6928 | [11 empty] | 144 | 18 | 48.1111 | 384.8889
| Supplier User Interface |  |  |  |  | 3008 | [11 empty] | 64 | 8 | 47 | 376
R2-13 | Develop UI components that allow suppliers to post new products to the marketplace | FTE (2) | FED, JD | 2256 | 0 | 2256 |  |  |  | 24 | [6 empty] | 24 | 48 | 6 | 47 | 376
R2-14 | Test user interface to ensure that components correctly map to API endpoints | FTE (2) | FED, JD | 752 | 0 | 752 |  |  |  | 8 | [6 empty] | 8 | 16 | 2 | 47 | 376
| Medisail User Interface |  |  |  |  | 3920 | [11 empty] | 80 | 10 | 49 | 392
R2-15 | Develop UI components that allow Medisail employees to view analytics data rendered from API endpoints connected to new database tables | FTE (2) | FED, JD | 2416 | 0 | 2416 |  |  |  | 32 | [6 empty] | 16 | 48 | 6 | 50.3333 | 402.6667
R2-16 | Test user interface to ensure that components correct map to API endpoints | FTE (2) | FED, JD | 1504 | 0 | 1504 |  |  |  | 16 | [6 empty] | 16 | 32 | 4 | 47 | 376
| Documentation |  |  | 0 |  | 2720 | [11 empty] | 40 | 5 | 68 | 544
R2-17 | Write documentation for integrated system | FTE (2) | SRD, ITM | 2720 | 0 | 2720 |  | 20 |  |  |  |  | 20 |  |  |  |  | 40 | 5 | 68 | 544
| Test Integrated System |  |  |  |  | 42678 | [11 empty] | 894 | 111.75 | 47.7383 | 381.906
| Unit Testing |  |  |  |  | 13496 | [11 empty] | 304 | 38 | 44.3947 | 355.1579
R2-18 | Write unit tests for new server functionality | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 | [5 empty] | 8 | 1 | 50 | 400
R2-19 | Write unit tests for new Medisail API interface endpoints | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R2-20 | Write unit tests for user API interface that ensure that customers don't have access to posting new products | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R2-21 | Write tests for customer user interface | FTE (2) | QAT1, QAT2 | 100 | 0 | 100 | [5 empty] | 2 |  |  |  | 2 |  | 4 | 0.5 | 25 | 200
R2-22 | Write tests for supplier user interface marketplace product posting rendering capabilities | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R2-23 | Write tests for Medisail user interface data analytics rendering capabilities | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R2-24 | Write tests for marketplace interface to ensure that new product postings are correctly rendered | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R2-25 | Write tests for shopping cart interface | FTE (2) | QAT1, QAT2 | 100 | 0 | 100 | [5 empty] | 2 |  |  |  | 2 |  | 4 | 0.5 | 25 | 200
R2-26 | Conduct back end unit tests | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R2-27 | Conduct user interface tests | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R2-28 | Communicate results of unit tests with development team | FTE (4) | QAT1, QAT2, ITM, SRD | 2976 | 0 | 2976 |  | 16 |  |  |  | 16 | 16 |  |  | 16 |  | 64 | 8 | 46.5 | 372
R2-29 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 7320 | 0 | 7320 |  | 40 | 40 | 40 | [7 empty] | 120 | 15 | 61 | 488
R2-30 | Retest user interfaces | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R2-31 | Reteset back end | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
| Integration Testing |  |  |  |  | 13878 | [11 empty] | 294 | 36.75 | 47.2041 | 377.6327
R2-32 | Write integration tests between supplier user interface and server | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R2-33 | Write integration tests between Medisail user interface and server | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R2-34 | Write integration tests between marketplace user interface and server | FTE (2) | QAT1, QAT2 | 100 | 0 | 100 | [5 empty] | 2 |  |  |  | 2 |  | 4 | 0.5 | 25 | 200
R2-35 | Write integration tests between user API interface and database | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R2-36 | Write integration tests between Medisail API interface and database | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R2-37 | Write mocked integration tests between user interfaces and database | FTE (2) | QAT1, QAT2 | 50 | 0 | 50 | [5 empty] | 1 |  |  |  | 1 |  | 2 | 0.25 | 25 | 200
R2-38 | Conduct integration tests between user interfaces and server | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R2-39 | Conduct integration tests between server and database | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R2-40 | Conduct integration tests between user interfaces and database | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R2-41 | Communicate results of integration tests with development team | FTE (4) | QAT1, QAT2, ITM, SRD | 1488 | 0 | 1488 |  | 8 |  |  |  | 8 | 8 |  |  | 8 |  | 32 | 4 | 46.5 | 372
R2-42 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 9840 | 0 | 9840 |  | 60 | 60 | 40 | [5 empty] | 0 |  | 160 | 20 | 61.5 | 492
R2-43 | Retest integration between user interface and server | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R2-44 | Retest integration between server and database | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R2-45 | Retest integration between user interface and database | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
| System Testing |  |  |  |  | 15304 | [11 empty] | 296 | 37 | 51.7027 | 413.6216
R2-46 | Write system tests of the entire integrated system | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R2-47 | Conduct system tests of the integrated system | FTE (4) | QAT1, QAT2, SRD, PM | 800 | 0 | 800 | [5 empty] | 16 |  |  |  | 16 |  | 32 | 4 | 25 | 200
R2-48 | Communicate results of system tests with development teams | FTE (4) | QAT1, QAT2, SRD, PM | 944 | 544 | 1488 | 8 | 8 |  |  |  | 8 |  |  |  | 8 |  | 32 | 4 | 46.5 | 372
R2-49 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 9840 | 0 | 9840 |  | 60 | 60 | 40 | [7 empty] | 160 | 20 | 61.5 | 492
R2-50 | Reconduct system tests | FTE (4) | QAT1, QAT2, SRD, PM | 1688 | 1088 | 2776 | 16 | 16 |  |  |  | 12 |  |  |  | 12 |  | 56 | 7 | 49.5714 | 396.5714
| Deploy Release 2 |  |  |  |  | 9323 | [11 empty] | 141 | 17.625 | 66.1206 | 528.9645
| Conduct Required Trainings |  |  |  |  | 3728 | [11 empty] | 56 | 7 | 66.5714 | 532.5714
R2-51 | Update sales manager on new capabilities of integrated e-procurement system | FTE (2) | PM, SM | 1008 | 1088 | 2096 | 16 | [6 empty] | 16 |  |  |  | 32 | 4 | 65.5 | 524
R2-52 | Train Medisail non-technical employees on integrated e-procurement system analytics capabilities | FTE (1) | PM |  | 1632 | 1632 | 24 | [10 empty] | 24 | 3 | 68 | 544
| Pre-Deployment Marketing |  |  |  |  | 504 | [11 empty] | 8 | 1 | 63 | 504
R2-53 | Create advertisement materials for integrated product | FTE (1) | SM | 504 | 0 | 504 | [7 empty] | 8 |  |  |  | 8 | 1 | 63 | 504
| Product Deployment |  |  |  |  | 3264 | [11 empty] | 48 | 6 | 68 | 544
R2-54 | Deploy integrated system | FTE (1) | SRD | 544 | 0 | 544 |  | 8 | [9 empty] | 8 | 1 | 68 | 544
R2-55 | Monitor system performance after deployment | FTE (1) | SRD | 2720 | 0 | 2720 |  | 40 | [9 empty] | 40 | 5 | 68 | 544
| Collect Supplier Feedback on Analytics Capabilities |  |  |  |  | 1827 | [11 empty] | 29 | 3.625 | 63 | 504
R2-56 | Create Medisail non-technical employee survey about new analytics capabilities | FTE (1) | SM | 126 | 0 | 126 | [7 empty] | 2 |  |  |  | 2 | 0.25 | 63 | 504
R2-57 | Create new customer survey with refined prompts based on results of Release 1 survey | FTE (1) | SM | 126 | 0 | 126 | [7 empty] | 2 |  |  |  | 2 | 0.25 | 63 | 504
R2-58 | Send survey to Medisail non-technical employees who use the system | FTE (1) | SM | 252 | 0 | 252 | [7 empty] | 4 |  |  |  | 4 | 0.5 | 63 | 504
R2-59 | Send revised survey to customers | FTE (1) | SM | 63 | 0 | 63 | [7 empty] | 1 |  |  |  | 1 | 0.125 | 63 | 504
R2-60 | Collect and analyze feedback | FTE (1) | SM | 1008 | 0 | 1008 | [7 empty] | 16 |  |  |  | 16 | 2 | 63 | 504
R2-61 | Share survey feedback with team | FTE (1) | SM | 252 | 0 | 252 | [7 empty] | 4 |  |  |  | 4 | 0.5 | 63 | 504
| Release 3: Advanced System |  |  |  |  | 107408 | [11 empty] | 2236 | 279.5 | 48.0358 | 384.2862
| Adjust Plan Based on Supplier Feedback |  |  |  |  | 2176 | [11 empty] | 32 | 4 | 68 | 544
R3-1 | Determine which aspects of feedback are relevant | FTE (2) | PM, SRD | 544 | 544 | 1088 | 8 | 8 | [9 empty] | 16 | 2 | 68 | 544
R3-2 | Revise Release 3 requirements based on feedback assessment | FTE (2) | PM, SRD | 544 | 544 | 1088 | 8 | 8 | [9 empty] | 16 | 2 | 68 | 544
| Update Backend for Advanced Analytics |  |  |  |  | 15096 | [11 empty] | 320 | 40 | 47.175 | 377.4
| User API Interface |  |  |  |  | 3896 | [11 empty] | 92 | 11.5 | 42.3478 | 338.7826
R3-3 | Write SQL queries to query analytics data from database for suppliers | FTE (1) | DBA | 544 | 0 | 544 |  |  |  |  | 16 | [6 empty] | 16 | 2 | 34 | 272
R3-4 | Write SQL queries to query analytics data from database for customers | FTE (1) | DBA | 544 | 0 | 544 |  |  |  |  | 16 | [6 empty] | 16 | 2 | 34 | 272
R3-5 | Create endpoints for analytics data for supplier UI | FTE (2) | BED, JD | 612 | 0 | 612 |  |  | 8 | [7 empty] | 4 | 12 | 1.5 | 51 | 408
R3-6 | Create endpoints for analytics data for user UI | FTE (2) | BED, JD | 612 | 0 | 612 |  |  | 8 | [7 empty] | 4 | 12 | 1.5 | 51 | 408
R3-7 | Test endpoints to ensure that supplier and user analytics data is mapped correctly | FTE (2) | BED, JD | 1584 | 0 | 1584 |  |  | 12 | [7 empty] | 24 | 36 | 4.5 | 44 | 352
| Tableau Functionality |  |  |  |  | 11200 | [11 empty] | 228 | 28.5 | 49.1228 | 392.9825
R3-8 | Negotiate and obtain Tableau licence | FTE (1) | PM | 0 | 2720 | 2720 | 40 | [10 empty] | 40 | 5 | 68 | 544
R3-9 | Review Tableau documentation | FTE (2) | DBA, BED | 2208 | 0 | 2208 |  |  | 24 |  | 24 | [6 empty] | 48 | 6 | 46 | 368
R3-10 | Refine database tables as needed per Tableau documentation | FTE (1) | DBA | 1088 | 0 | 1088 |  |  |  |  | 32 | [6 empty] | 32 | 4 | 34 | 272
R3-11 | Create Tableau-specific API endpoints for suppliers | FTE (2) | BED, JD | 992 | 0 | 992 |  |  | 12 | [7 empty] | 8 | 20 | 2.5 | 49.6 | 396.8
R3-12 | Create Tableau-specific API endpoints for customers | FTE (2) | BED, JD | 992 | 0 | 992 |  |  | 12 | [7 empty] | 8 | 20 | 2.5 | 49.6 | 396.8
R3-13 | Create Tableau-specific API endpoints for Medisail non-technical employees | FTE (2) | BED, JD | 992 | 0 | 992 |  |  | 12 | [7 empty] | 8 | 20 | 2.5 | 49.6 | 396.8
R3-14 | Test all Tableau endpoints | FTE (2) | DBA, BED | 2208 | 0 | 2208 |  |  | 24 |  | 24 | [6 empty] | 48 | 6 | 46 | 368
| Update Frontend for Advanced Analytics |  |  |  |  | 19392 | [11 empty] | 332 | 41.5 | 58.4096 | 467.2771
R3-15 | Create UI components in customer user interface to render analytics data from database | FTE (2) | FED, JD | 2872 | 0 | 2872 |  |  |  | 40 | [6 empty] | 16 | 56 | 7 | 51.2857 | 410.2857
R3-16 | Create UI components in customer user interface to render Tableau graphics and charts | FTE (2) | FED, SRD | 3000 | 0 | 3000 |  | 24 |  | 24 | [7 empty] | 48 | 6 | 62.5 | 500
R3-17 | Create UI components in supplier user interface to render analytics data from database | FTE (2) | FED, JD | 3020 | 0 | 3020 |  |  |  | 40 | [6 empty] | 20 | 60 | 7.5 | 50.3333 | 402.6667
R3-18 | Create UI components in supplier user interface to render Tableau graphics and charts | FTE (2) | FED, SRD | 3000 | 0 | 3000 |  | 24 |  | 24 | [7 empty] | 48 | 6 | 62.5 | 500
R3-19 | Create UI components in Medisail user interface to render Tableau graphics and charts | FTE (2) | FED, SRD | 3000 | 0 | 3000 |  | 24 |  | 24 | [7 empty] | 48 | 6 | 62.5 | 500
R3-20 | Test database analytics rendering in customer and supplier user interfaces | FTE (2) | FED, SRD | 2000 | 0 | 2000 |  | 16 |  | 16 | [7 empty] | 32 | 4 | 62.5 | 500
R3-21 | Test Tableau integration in all user interfaces | FTE (2) | FED, SRD | 2500 | 0 | 2500 |  | 20 |  | 20 | [7 empty] | 40 | 5 | 62.5 | 500
| Documentation |  |  |  |  | 5440 | [11 empty] | 80 | 10 | 68 | 544
R3-22 | Write documentation for advanced system | FTE (2) | SRD, ITM | 5440 | 0 | 5440 |  | 40 |  |  |  |  | 40 |  |  |  |  | 80 | 10 | 68 | 544
| Test Advanced System |  |  |  |  | 55368 | [11 empty] | 1320 | 165 | 41.9455 | 335.5636
| Unit Testing |  |  |  |  | 16584 | [11 empty] | 456 | 57 | 36.3684 | 290.9474
R3-23 | Write unit tests for data analytics API endpoints to ensure that only applicable data is accessible | FTE (2) | QAT1, QAT2 | 300 | 0 | 300 | [5 empty] | 6 |  |  |  | 6 |  | 12 | 1.5 | 25 | 200
R3-24 | Write unit tests for Tableau API endpoints | FTE (2) | QAT1, QAT2 | 300 | 0 | 300 | [5 empty] | 6 |  |  |  | 6 |  | 12 | 1.5 | 25 | 200
R3-25 | Write unit tests for new Medisail API interface endpoints to ensure that all data analytics is accessable | FTE (2) | QAT1, QAT2 | 300 | 0 | 300 | [5 empty] | 6 |  |  |  | 6 |  | 12 | 1.5 | 25 | 200
R3-26 | Write tests for customer user interface data analytics capabilities | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R3-27 | Write tests for supplier user interface data analytics capabilities | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R3-28 | Write tests for Medisail user interface data analytics rendering capabilities | FTE (2) | QAT1, QAT2 | 500 | 0 | 500 | [5 empty] | 10 |  |  |  | 10 |  | 20 | 2.5 | 25 | 200
R3-29 | Write tests for Tableau integration in customer user interface | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R3-30 | Write tests for Tableau integration in supplier user interface | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R3-31 | Write tests for Tableau integration in Medisail user interface | FTE (2) | QAT1, QAT2 | 800 | 0 | 800 | [5 empty] | 16 |  |  |  | 16 |  | 32 | 4 | 25 | 200
R3-32 | Conduct back end unit tests | FTE (2) | QAT1, QAT2 | 1600 | 0 | 1600 | [5 empty] | 32 |  |  |  | 32 |  | 64 | 8 | 25 | 200
R3-33 | Conduct user interface tests | FTE (2) | QAT1, QAT2 | 1200 | 0 | 1200 | [5 empty] | 24 |  |  |  | 24 |  | 48 | 6 | 25 | 200
R3-34 | Communicate results of unit tests with development team | FTE (4) | QAT1, QAT2, ITM, SRD | 1864 | 0 | 1864 |  | 8 | 8 | 8 |  | 8 |  |  |  | 8 |  | 40 | 5 | 46.6 | 372.8
R3-35 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 7320 | 0 | 7320 |  | 40 | 40 | 40 | [5 empty] | 0 |  | 120 | 15 | 61 | 488
R3-36 | Retest user interfaces | FTE (2) | QAT1, QAT2 | 600 | 0 | 600 | [5 empty] | 12 |  |  |  | 12 |  | 24 | 3 | 25 | 200
R3-37 | Reteset back end | FTE (2) | QAT1, QAT2 | 600 | 0 | 600 | [5 empty] | 12 |  |  |  | 12 |  | 24 | 3 | 25 | 200
| Integration Testing |  |  |  |  | 17568 | [11 empty] | 416 | 52 | 42.2308 | 337.8462
R3-38 | Write integration tests between supplier user interface and server | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R3-39 | Write integration tests between Medisail user interface and server | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R3-40 | Write integration tests between marketplace user interface and server | FTE (2) | QAT1, QAT2 | 400 | 0 | 400 | [5 empty] | 8 |  |  |  | 8 |  | 16 | 2 | 25 | 200
R3-41 | Write integration tests between user API interface and database | FTE (2) | QAT1, QAT2 | 600 | 0 | 600 | [5 empty] | 12 |  |  |  | 12 |  | 24 | 3 | 25 | 200
R3-42 | Write integration tests between Medisail API interface and database | FTE (2) | QAT1, QAT2 | 600 | 0 | 600 | [5 empty] | 12 |  |  |  | 12 |  | 24 | 3 | 25 | 200
R3-43 | Write mocked integration tests between user interfaces and database | FTE (2) | QAT1, QAT2 | 300 | 0 | 300 | [5 empty] | 6 |  |  |  | 6 |  | 12 | 1.5 | 25 | 200
R3-44 | Conduct integration tests between user interfaces and server | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R3-45 | Conduct integration tests between server and database | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R3-46 | Conduct integration tests between user interfaces and database | FTE (2) | QAT1, QAT2 | 200 | 0 | 200 | [5 empty] | 4 |  |  |  | 4 |  | 8 | 1 | 25 | 200
R3-47 | Communicate results of integration tests with development team | FTE (4) | QAT1, QAT2, ITM, SRD | 1488 | 0 | 1488 |  | 8 |  |  |  | 8 | 8 |  |  | 8 |  | 32 | 4 | 46.5 | 372
R3-48 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 10980 | 0 | 10980 |  | 60 | 60 | 60 | [5 empty] | 0 |  | 180 | 22.5 | 61 | 488
R3-49 | Retest integration between user interface and server | FTE (2) | QAT1, QAT2 | 600 | 0 | 600 | [5 empty] | 12 |  |  |  | 12 |  | 24 | 3 | 25 | 200
R3-50 | Retest integration between server and database | FTE (2) | QAT1, QAT2 | 600 | 0 | 600 | [5 empty] | 12 |  |  |  | 12 |  | 24 | 3 | 25 | 200
R3-51 | Retest integration between user interface and database | FTE (2) | QAT1, QAT2 | 600 | 0 | 600 | [5 empty] | 12 |  |  |  | 12 |  | 24 | 3 | 25 | 200
| System Testing | FTE (2) | QAT1, QAT2 |  |  | 21216 | [9 empty] | 0 |  | 448 | 56 | 47.3571 | 378.8571
R3-52 | Write system tests of the entire advanced system | FTE (2) | QAT1, QAT2 | 1200 | 0 | 1200 | [5 empty] | 24 |  |  |  | 24 |  | 48 | 6 | 25 | 200
R3-53 | Conduct system tests of the advanced system | FTE (4) | QAT1, QAT2, SRD, PM | 800 | 0 | 800 | [5 empty] | 16 |  |  |  | 16 |  | 32 | 4 | 25 | 200
R3-54 | Communicate results of system tests with development teams | FTE (4) | QAT1, QAT2, SRD, PM | 1888 | 1088 | 2976 | 16 | 16 |  |  |  | 16 |  |  |  | 16 |  | 64 | 8 | 46.5 | 372
R3-55 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 14640 | 0 | 14640 |  | 80 | 80 | 80 | [5 empty] | 0 |  | 240 | 30 | 61 | 488
R3-56 | Reconduct system tests | FTE (4) | QAT1, QAT2, SRD, PM | 1600 | 0 | 1600 | [5 empty] | 32 |  |  |  | 32 |  | 64 | 8 | 25 | 200
| Deploy Release 3 |  |  |  |  | 9936 | [11 empty] | 152 | 19 | 65.3684 | 522.9474
| Conduct Required Trainings |  |  |  |  | 5664 | [11 empty] | 88 | 11 | 64.3636 | 514.9091
R3-57 | Update sales manager on new capabilities of advanced e-procurement system | FTE (2) | PM, SM | 1512 | 1632 | 3144 | 24 | [6 empty] | 24 |  |  |  | 48 | 6 | 65.5 | 524
R3-58 | Train Medisail non-technical employees on new analytics capabilities | FTE (1) | PM | 1008 | 0 | 1008 | [7 empty] | 16 |  |  |  | 16 | 2 | 63 | 504
R3-59 | Train customers on new analytics capabilities | FTE (1) | PM | 756 | 0 | 756 | [7 empty] | 12 |  |  |  | 12 | 1.5 | 63 | 504
R3-60 | Train suppliers on new analytics capabilities | FTE (1) | PM | 756 | 0 | 756 | [7 empty] | 12 |  |  |  | 12 | 1.5 | 63 | 504
| Pre-Deployment Marketing |  |  |  |  | 1008 | [11 empty] | 16 | 2 | 63 | 504
R3-61 | Create advertisement materials for advanced product | FTE (1) | SM | 504 | 0 | 504 | [7 empty] | 8 |  |  |  | 8 | 1 | 63 | 504
R3-62 | Conduct sales calls with potential new customers | FTE (1) | SM | 504 | 0 | 504 | [7 empty] | 8 |  |  |  | 8 | 1 | 63 | 504
| Product Deployment |  |  |  | 0 | 3264 | [11 empty] | 48 | 6 | 68 | 544
R3-63 | Deploy advanced system | FTE (1) | SRD | 544 | 0 | 544 |  | 8 | [9 empty] | 8 | 1 | 68 | 544
R3-64 | Monitor system performance after deployment | FTE (1) | SRD | 2720 | 0 | 2720 |  | 40 | [9 empty] | 40 | 5 | 68 | 544
| End of Project Activities |  |  |  |  | 20560 | [11 empty] | 340 | 42.5 | 60.4706 | 483.7647
| Product Adoption |  |  |  |  | 6818 | [11 empty] | 106 | 13.25 | 64.3208 | 514.566
EOP-1 | Plan product education workshops for customers and suppliers | FTE (2) | PM, SM | 756 | 816 | 1572 | 12 | [6 empty] | 12 |  |  |  | 24 | 3 | 65.5 | 524
EOP-2 | Schedule product education workshops | FTE (1) | SM | 126 | 0 | 126 | [7 empty] | 2 |  |  |  | 2 | 0.25 | 63 | 504
EOP-3 | Conduct product education workshops | FTE (1) | SM | 2520 | 0 | 2520 | [7 empty] | 40 |  |  |  | 40 | 5 | 63 | 504
EOP-4 | Gather feedback from customers and suppliers during workshops | FTE (1) | SM | 504 | 0 | 504 | [7 empty] | 8 |  |  |  | 8 | 1 | 63 | 504
EOP-5 | Train Medisail sales teams and customer support on product | FTE (2) | PM, SM | 1008 | 1088 | 2096 | 16 | [6 empty] | 16 |  |  |  | 32 | 4 | 65.5 | 524
| Continuous Improvement |  |  |  |  | 13742 | [11 empty] | 234 | 29.25 | 58.7265 | 469.812
EOP-6 | Send monthly surveys to customers and suppliers | FTE (1) | SM | 126 | 0 | 126 | [7 empty] | 2 |  |  |  | 2 | 0.25 | 63 | 504
EOP-7 | Gather feedback from surveys | FTE (1) | SM | 504 | 0 | 504 | [7 empty] | 8 |  |  |  | 8 | 1 | 63 | 504
EOP-8 | Discuss results of surveys | FTE (2) | PM, SM | 504 | 544 | 1048 | 8 | [6 empty] | 8 |  |  |  | 16 | 2 | 65.5 | 524
EOP-9 | Determine feasibility of improvements suggested in survey results | FTE (3) | PM, SRD, ITM | 2176 | 1088 | 3264 | 16 | 16 |  |  |  |  | 16 |  |  |  |  | 48 | 6 | 68 | 544
EOP-10 | Implement accepted improvements to software system | FTE (4) | SRD, BED, FED, JD | 8800 | 0 | 8800 |  | 40 | 40 | 40 | [6 empty] | 40 | 160 | 20 | 55 | 440
|  | Total |  | 276755 | 31212 | 307967 | 459 | 1117 | 826 | 918 | 253 | 806 | 169 | 334 | 0 | 798 | 517 | 6197 | 774.625 | 53.6289 | 429.0316
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I've locked the spreadsheet to prevent accidental changes because there are a lot of formulas and the sheets all link together. If anyone wants to make a change, please let me know

## Total Cost of Ownership
Costs of Implementing e-Procurement System | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Licenses
Tableau yearly license (billed at $42/month) | 504 | 504 | 504 | 504 | 504 | 504 | 3024
Oracle DBMS license (billed at $950/year) | 950 | 950 | 950 | 950 | 950 | 950 | 5700
Product Support
Server center rental | 204204 | 204204 | 204204 | 204204 | 204204 | 204204 | 1225224
Product maintenence | 0 | 40000 | 40000 | 40000 | 40000 | 40000 | 200000
System Support
System use training | 0 | 40000 | 30000 | 20000 | 10000 | 5000 | 105000
System enhancement and upgrade costs | 0 | 111548.2133 | 111548.2133 | 111548.2133 | 111548.2133 | 111548.2133 | 557741.0667
System downtime costs | 48000 | 57600 | 74880 | 101088 | 116251.2 | 127876.32 | 525695.52
Technical support | 0 | 52000 | 53040 | 54100.8 | 55182.816 | 56286.4723 | 270610.0883
Contracts
Distribution contracts | 33600 | 67200 | 73920 | 81312 | 89443.2 | 98387.52 | 443862.72
Total Indirect Costs | 287258 | 574006.2133 | 589046.2133 | 613707.0133 | 628083.4293 | 644756.5257 | 3336857.395
Product Development
Total labor development cost | 307967 | 0 | 0 | 0 | 0 | 0 | 307967
Total Cost of Ownership | 595225 | 574006.2133 | 589046.2133 | 613707.0133 | 628083.4293 | 644756.5257 | 3644824.395
Overhead Calculation Sum of Indirect Costs / Sum of Direct Labor Costs | 10.8351
Overhead Multiplier | 1.1084
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I've locked the spreadsheet to prevent accidental changes because there are a lot of formulas and the sheets all link together. If anyone wants to make a change, please let me know

## Project Software Cost
Overhead multiplier: |  |  |  |  | 1.1084 | 1.1084
Task Number | Task Name | Resource Type | Resource Name | Team Estimate | PM Estimate | Cost of Component, Phase, or Sub Phase | PM Hours | SRD Hours | BED Hours | FED Hours | DBA Hours | QAT1Hours | ITM Hours | SM Hours | SA Hours | QAT2 Hours | JD Hours | Duration (Hours) | Duration (Days) | Hourly Rate (per task and average) | Daily Rate (per task and average) | Development Cost with Overhead | % Total Cost of Phase | % Total Cost of Project
| Pre-Development Activities |  |  |  |  | 10424 | [11 empty] | 171 | 21.375 | 60.9591 | 487.6725 | 11553.4522 | 100% | 3.385%
| Requirements Analysis |  |  |  |  | 5304 | [11 empty] | 78 | 9.75 | 68 | 544 | 5878.6944 | 50.88% | 1.722%
PDA-1 | Gather requirements from stakeholders | FTE (1) | PM | 0 | 2720 | 2720 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 5 | 68 | 544 | 3014.7151 | 26.09% | 0.8832%
PDA-2 | Create software system requirements analysis | FTE (3) | PM, ITM, SRD | 1360 | 680 | 2040 | 10 | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 30 | 3.75 | 68 | 544 | 2261.0363 | 19.57% | 0.6624%
PDA-3 | Receive approval of requirements analysis | FTE (1) | PM | 0 | 544 | 544 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 68 | 544 | 602.943 | 5.219% | 0.1766%
| Feasibility Study |  |  | 0 | 0 | 2380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 4.375 | 68 | 544 | 2637.8757 | 22.83% | 0.7728%
PDA-4 | Conduct cash flow analysis | FTE (1) | PM | 0 | 1360 | 1360 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 2.5 | 68 | 544 | 1507.3575 | 13.05% | 0.4416%
PDA-5 | Conduct risk assessment | FTE (1) | PM | 0 | 1020 | 1020 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1.875 | 68 | 544 | 1130.5182 | 9.785% | 0.3312%
| Development Environment Setup |  |  |  |  | 2740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 7.25 | 47.2414 | 377.931 | 3036.8821 | 26.29% | 0.8897%
PDA-5 | Update laptops to Windows 11 OS | FTE (7) | PM, ITM, SRD, BED, FED, DBA, QAT | 620 | 136 | 880 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 18 | 2.25 | 48.8889 | 391.1111 | 975.349 | 8.442% | 0.2857%
PDA-6 | Install and configure Visual Studio Code | FTE (6) | ITM, SRD, BED, FED, DBA, QAT | 310 | 0 | 372 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 8 | 1 | 46.5 | 372 | 412.3066 | 3.569% | 0.1208%
PDA-7 | Install and configure Postman, Maven, and Junit 5 testing software | FTE (6) | ITM, SRD, BED, FED, DBA, QAT | 620 | 0 | 744 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 16 | 2 | 46.5 | 372 | 824.6132 | 7.137% | 0.2416%
PDA-8 | Install and configure PostgreSQL and SQL interface | FTE (6) | ITM, SRD, BED, FED, DBA, QAT | 620 | 0 | 744 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 16 | 2 | 46.5 | 372 | 824.6132 | 7.137% | 0.2416%
| Release 1: Basic (Core) System |  |  |  |  | 97340 | [11 empty] | 2018 | 252.25 | 48.2359 | 385.887 | 107886.8995 | 100% | 31.61%
| Mock Up User Interfaces |  |  |  |  | 2397 | [11 empty] | 61 | 7.625 | 39.2951 | 314.3607 | 2656.7177 | 2.463% | 0.7783%
R1-1 | Mock up user interface for Medisail customers | FTE (1) | FED | 57 | 0 | 501 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13 | 1.625 | 38.5385 | 308.3077 | 555.2839 | 0.5147% | 0.1627%
R1-2 | Mock up user interface for suppliers | FTE (1) | FED | 57 | 0 | 501 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13 | 1.625 | 38.5385 | 308.3077 | 555.2839 | 0.5147% | 0.1627%
R1-3 | Mock up user interface for Medisail non-technical employees | FTE (1) | FED | 57 | 0 | 353 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9 | 1.125 | 39.2222 | 313.7778 | 391.248 | 0.3626% | 0.1146%
R1-4 | Mock up marketplace user interface | FTE (1) | FED | 114 | 0 | 558 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 14 | 1.75 | 39.8571 | 318.8571 | 618.4599 | 0.5732% | 0.1812%
R1-5 | Mock up shopping cart and checkout interfaces | FTE (1) | FED | 57 | 0 | 353 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9 | 1.125 | 39.2222 | 313.7778 | 391.248 | 0.3626% | 0.1146%
R1-6 | Mock up login portal user interface | FTE (1) | FED | 57 | 0 | 131 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0.375 | 43.6667 | 349.3333 | 145.194 | 0.1346% | 0.04254%
| Database Creation |  |  |  |  | 1632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 6 | 34 | 272 | 1808.8291 | 1.677% | 0.5299%
R1-7 | Create database | FTE (1) | DBA | 136 | 0 | 136 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0.5 | 34 | 272 | 150.7358 | 0.1397% | 0.04416%
R1-8 | Create tables with associated fields | FTE (1) | DBA | 136 | 0 | 136 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0.5 | 34 | 272 | 150.7358 | 0.1397% | 0.04416%
| Fill Inventory, Supplier, Distributor, and Customer Tables with Dummy Data |  |  |  |  | 1360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 5 | 34 | 272 | 1507.3575 | 1.397% | 0.4416%
R1-9 | Fill Medical Supplies table with dummy data | FTE (1) | DBA | 272 | 0 | 272 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 34 | 272 | 301.4715 | 0.2794% | 0.08832%
R1-10 | Fill Medical Supplier table with dummy data | FTE (1) | DBA | 272 | 0 | 272 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 34 | 272 | 301.4715 | 0.2794% | 0.08832%
R1-11 | Fill Distributor table with dummy data | FTE (1) | DBA | 272 | 0 | 272 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 34 | 272 | 301.4715 | 0.2794% | 0.08832%
R1-12 | Fill Customer table with dummy data | FTE (1) | DBA | 272 | 0 | 272 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 34 | 272 | 301.4715 | 0.2794% | 0.08832%
R1-13 | Write SQL script to designate primary and foreign keys of each table in the database | FTE(1) | DBA | 272 | 0 | 272 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 34 | 272 | 301.4715 | 0.2794% | 0.08832%
| Create Server and API Interfaces |  |  |  |  | 3748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 10.25 | 45.7073 | 365.6585 | 4154.1001 | 3.85% | 1.217%
R1-14 | Develop core functionalities of RESTful server | FTE (1) | BED | 696 | 0 | 1288 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 28 | 3.5 | 46 | 368 | 1427.5563 | 1.323% | 0.4182%
R1-15 | Create API endpoints for user API interface | FTE (1) | BED | 58 | 0 | 502 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13 | 1.625 | 38.6154 | 308.9231 | 556.3923 | 0.5157% | 0.163%
R1-16 | Create API endpoints for Medisail API interface | FTE (1) | BED | 58 | 0 | 502 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13 | 1.625 | 38.6154 | 308.9231 | 556.3923 | 0.5157% | 0.163%
R1-17 | Write SQL script to query data from Inventory Database | FTE (1) | BED | 928 | 0 | 928 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2 | 58 | 464 | 1028.5499 | 0.9534% | 0.3013%
R1-18 | Test endpoints in Postman | FTE (1) | BED | 232 | 0 | 528 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 12 | 1.5 | 44 | 352 | 585.2094 | 0.5424% | 0.1714%
| Database Modification |  |  |  |  | 2256 | [11 empty] | 66 | 8.25 | 34.1818 | 273.4545 | 2500.4402 | 2.318% | 0.7325%
| Fill Inventory, Supplier, Distributor, and Customer Tables with Authentic Data |  |  |  |  | 2256 | [11 empty] | 66 | 8.25 | 34.1818 | 273.4545 | 2500.4402 | 2.318% | 0.7325%
R1-19 | Fill Medical Supplies table with data in fields: Inventory SKU Number (Integer), Item Name (String), Manufacturer (String), Listing Price (float), Supplier Name (String), Expiration Date (date), Generic Medicine (boolean), Brand Name Medicine (boolean) | FTE (1) | DBA | 408 | 0 | 408 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.5 | 34 | 272 | 452.2073 | 0.4191% | 0.1325%
R1-20 | Fill Medical Supplier table with data in fields: Supplier ID (Integer), Supplier Name (String), Supplier Primary Address (String), Phone Number (String), Supplier Email (String), Better Business Bureau Rating (String), General Notes (String) | FTE (1) | DBA | 408 | 0 | 408 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.5 | 34 | 272 | 452.2073 | 0.4191% | 0.1325%
R1-21 | Fill Distributor table with data in fields: Distributor ID (Integer), Distributor Name (String), Distributor Primary Address (String), Phone Number (String), Distributor Email (String), Better Business Bureau Rating (String), General Notes (String) | FTE (1) | DBA | 408 | 0 | 408 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.5 | 34 | 272 | 452.2073 | 0.4191% | 0.1325%
R1-22 | Fill Customer table with data in fields: Customer ID (Integer), Customer Name (String), Subscription Tier (Integer), Item Purchased (String), Customer Primary Address (String), Phone Number (String), Customer Email (String), | FTE (1) | DBA | 408 | 0 | 408 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.5 | 34 | 272 | 452.2073 | 0.4191% | 0.1325%
R1-23 | Revise SQL script to query authentic data | FTE (1) | DBA | 408 | 0 | 408 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.5 | 34 | 272 | 452.2073 | 0.4191% | 0.1325%
R1-24 | Retest API endpoints in Postman to ensure that authentic data is correctly accessed | FTE (1) | BED | 68 | 0 | 216 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 0.75 | 36 | 288 | 239.4038 | 0.2219% | 0.07014%
| Implement User Interfaces |  |  |  |  | 10048 | [11 empty] | 224 | 28 | 44.8571 | 358.8571 | 11136.7122 | 10.32% | 3.263%
R1-25 | Develop marketplace user interface | FTE (1) | FED | 912 | 0 | 1800 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 40 | 5 | 45 | 360 | 1995.032 | 1.849% | 0.5845%
R1-26 | Develop customer user interface | FTE (1) | FED | 912 | 0 | 1800 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 40 | 5 | 45 | 360 | 1995.032 | 1.849% | 0.5845%
R1-27 | Develop shopping cart and checkout interface | FTE (1) | FED | 912 | 0 | 1800 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 40 | 5 | 45 | 360 | 1995.032 | 1.849% | 0.5845%
R1-28 | Develop supplier user interface | FTE (1) | FED | 912 | 0 | 1800 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 40 | 5 | 45 | 360 | 1995.032 | 1.849% | 0.5845%
R1-29 | Develop Medisail user interface | FTE (1) | FED | 912 | 0 | 1800 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 40 | 5 | 45 | 360 | 1995.032 | 1.849% | 0.5845%
R1-30 | Develop login interface | FTE (1) | FED | 456 | 0 | 1048 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 24 | 3 | 43.6667 | 349.3333 | 1161.552 | 1.077% | 0.3403%
| Documentation |  |  |  |  | 2720 | [11 empty] | 40 | 5 | 68 | 544 | 3014.7151 | 2.794% | 0.8832%
R1-31 | Write documentation for core system | FTE (2) | SRD, ITM | 2720 | 0 | 2720 | 0 | 20 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 40 | 5 | 68 | 544 | 3014.7151 | 2.794% | 0.8832%
| Test Core System |  |  |  |  | 61124 | [11 empty] | 1292 | 161.5 | 47.3096 | 378.4768 | 67746.8548 | 62.79% | 19.85%
| Unit Testing |  |  |  |  | 13908 | [11 empty] | 356 | 44.5 | 39.0674 | 312.5393 | 15414.9476 | 14.29% | 4.516%
R1-32 | Write unit tests for server | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.2055% | 0.06494%
R1-33 | Write unit tests for Medisail API interface | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.2055% | 0.06494%
R1-34 | Write unit tests for user API interface | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.2055% | 0.06494%
R1-35 | Write tests for customer user interface | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.4109% | 0.1299%
R1-36 | Write tests for supplier user interface | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.4109% | 0.1299%
R1-37 | Write tests for Medisail user interface | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.4109% | 0.1299%
R1-38 | Write tests for marketplace interface | FTE (1) | QAT | 300 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 0 | 24 | 3 | 25 | 200 | 665.0107 | 0.6164% | 0.1948%
R1-39 | Write tests for shopping cart interface | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.2055% | 0.06494%
R1-40 | Write tests for checkout interface | FTE (1) | QAT | 150 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6 | 0 | 12 | 1.5 | 25 | 200 | 332.5053 | 0.3082% | 0.09741%
R1-41 | Conduct back end unit tests | FTE (1) | QAT | 150 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6 | 0 | 12 | 1.5 | 25 | 200 | 332.5053 | 0.3082% | 0.09741%
R1-42 | Conduct user interface tests | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.4109% | 0.1299%
R1-43 | Communicate results of unit tests with development team | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.4109% | 0.1299%
R1-44 | Modify system based on test results (if needed) | FTE (1) | QAT | 150 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6 | 0 | 12 | 1.5 | 25 | 200 | 332.5053 | 0.3082% | 0.09741%
R1-45 | Retest user interfaces | FTE (3) | QAT, ITM, SRD | 744 | 544 | 1488 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 8 | 0 | 32 | 4 | 46.5 | 372 | 1649.2265 | 1.529% | 0.4832%
R1-46 | Reteset back end | FTE (3) | SRD, BED, FED | 7320 | 0 | 7320 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 15 | 61 | 488 | 8113.1303 | 7.52% | 2.377%
R1-47 | Retest user interfaces | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.4109% | 0.1299%
R1-48 | Reteset back end | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.4109% | 0.1299%
| Integration Testing |  |  |  |  | 19728 | [11 empty] | 416 | 52 | 47.4231 | 379.3846 | 21865.5512 | 20.27% | 6.406%
R1-49 | Write integration tests between user interfaces and server | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.4109% | 0.1299%
R1-44 | Write integration tests between server and database | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.4109% | 0.1299%
R1-45 | Write mocked integration tests between user interfaces and database | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.4109% | 0.1299%
R1-46 | Conduct integration tests between user interfaces and server | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.4109% | 0.1299%
R1-47 | Conduct integration tests between server and database | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.4109% | 0.1299%
R1-48 | Conduct integration tests between user interfaces and database | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.4109% | 0.1299%
R1-49 | Communicate results of integration tests with development team | FTE (3) | QAT, ITM, SRD | 744 | 544 | 1488 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 8 | 0 | 32 | 4 | 46.5 | 372 | 1649.2265 | 1.529% | 0.4832%
R1-50 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 14640 | 0 | 14640 | 0 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 30 | 61 | 488 | 16226.2606 | 15.04% | 4.754%
R1-51 | Retest integration between user interface and server | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.4109% | 0.1299%
R1-52 | Retest integration between server and database | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.4109% | 0.1299%
R1-53 | Retest integration between user interface and database | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.4109% | 0.1299%
| System Testing |  |  |  |  | 27488 | [11 empty] | 520 | 65 | 52.8615 | 422.8923 | 30466.356 | 28.24% | 8.926%
R1-54 | Write system tests of the entire core system | FTE (1) | QAT | 400 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0 | 32 | 4 | 25 | 200 | 886.6809 | 0.8219% | 0.2598%
R1-55 | Conduct system tests of the core system | FTE (3) | QAT, SRD, PM | 3720 | 2720 | 7440 | 40 | 40 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 160 | 20 | 46.5 | 372 | 8246.1324 | 7.643% | 2.416%
R1-56 | Communicate results of system tests with development teams | FTE (3) | QAT, SRD, PM | 1088 | 544 | 1632 | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 24 | 3 | 68 | 544 | 1808.8291 | 1.677% | 0.5299%
R1-57 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 14640 | 0 | 14640 | 0 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 30 | 61 | 488 | 16226.2606 | 15.04% | 4.754%
R1-58 | Reconduct system tests | FTE (3) | QAT, SRD, PM | 1488 | 1088 | 2976 | 16 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0 | 64 | 8 | 46.5 | 372 | 3298.453 | 3.057% | 0.9663%
| Deploy Release 1 |  |  |  |  | 13415 | [11 empty] | 205 | 25.625 | 65.439 | 523.5122 | 14868.5305 | 13.78% | 4.356%
| Conduct Required Trainings |  |  |  |  | 6328 | [11 empty] | 96 | 12 | 65.9167 | 527.3333 | 7013.646 | 6.501% | 2.055%
R1-60 | Train sales manager on core e-procurement system | FTE (2) | PM, SM | 2520 | 2720 | 5240 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 80 | 10 | 65.5 | 524 | 5807.7599 | 5.383% | 1.701%
R1-61 | Train Medisail non-technical employees on core e-procurement system | FTE (1) | PM | 0 | 1088 | 1088 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2 | 68 | 544 | 1205.886 | 1.118% | 0.3533%
| Pre-Deployment Marketing |  |  |  |  | 2520 | [11 empty] | 40 | 5 | 63 | 504 | 2793.0449 | 2.589% | 0.8183%
R1-61 | Create advertisement materials for core product | FTE (1) | SM | 1008 | 0 | 1008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 2 | 63 | 504 | 1117.2179 | 1.036% | 0.3273%
R1-62 | Identify pilot customers | FTE (1) | SM | 1512 | 0 | 1512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 3 | 63 | 504 | 1675.8269 | 1.553% | 0.491%
| Product Deployment |  |  |  |  | 2992 | [11 empty] | 44 | 5.5 | 68 | 544 | 3316.1866 | 3.074% | 0.9715%
R1-63 | Deploy core system | FTE (1) | SRD | 272 | 0 | 272 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0.5 | 68 | 544 | 301.4715 | 0.2794% | 0.08832%
R1-64 | Monitor system performance after deployment | FTE (1) | SRD | 2720 | 0 | 2720 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 5 | 68 | 544 | 3014.7151 | 2.794% | 0.8832%
| Collect Customer Feedback |  |  |  |  | 1575 | [11 empty] | 25 | 3.125 | 63 | 504 | 1745.653 | 1.618% | 0.5114%
R1-65 | Create customer survey | FTE (1) | SM | 252 | 0 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0.5 | 63 | 504 | 279.3045 | 0.2589% | 0.08183%
R1-66 | Send customer survey to pilot customers | FTE (1) | SM | 63 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0.125 | 63 | 504 | 69.8261 | 0.06472% | 0.02046%
R1-67 | Collect and analyze customer feedback | FTE (1) | SM | 1008 | 0 | 1008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 2 | 63 | 504 | 1117.2179 | 1.036% | 0.3273%
R1-68 | Share customer feedback with team | FTE (1) | SM | 252 | 0 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0.5 | 63 | 504 | 279.3045 | 0.2589% | 0.08183%
| Release 2: Integrated System |  |  |  |  | 72235 | [11 empty] | 1432 | 179 | 50.4434 | 403.5475 | 80061.7442 | 100% | 23.46%
| Adjust Plan Based on Customer Feedback |  |  |  |  | 2176 | [11 empty] | 32 | 4 | 68 | 544 | 2411.7721 | 3.012% | 0.7066%
R2-1 | Determine which aspects of feedback are relevant | FTE (2) | PM, SRD | 544 | 544 | 1088 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2 | 68 | 544 | 1205.886 | 1.506% | 0.3533%
R2-2 | Revise Release 2 requirements based on feedback assessment | FTE (2) | PM, SRD | 544 | 544 | 1088 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2 | 68 | 544 | 1205.886 | 1.506% | 0.3533%
| Modify Database Functionality |  |  |  |  | 1994 | [11 empty] | 53 | 6.625 | 37.6226 | 300.9811 | 2210.0522 | 2.76% | 0.6475%
| Make Static Tables Dynamic |  |  |  |  | 1178 | [11 empty] | 29 | 3.625 | 40.6207 | 324.9655 | 1305.6376 | 1.631% | 0.3825%
R2-3 | Update endpoints in server to allow for database updates | FTE (1) | BED | 232 | 0 | 824 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 20 | 2.5 | 41.2 | 329.6 | 913.2813 | 1.141% | 0.2676%
R2-4 | Test mock updates in database | FTE (1) | BED | 58 | 0 | 354 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9 | 1.125 | 39.3333 | 314.6667 | 392.3563 | 0.4901% | 0.1149%
| Create Customer Statistics Table |  |  |  |  | 272 | [11 empty] | 8 | 1 | 34 | 272 | 301.4715 | 0.3765% | 0.08832%
R2-5 | Fill Customer Statistics table with data in fields: Customer ID (Integer), Customer Name (String), Subscription Tier (Integer), Orders per Month (Integer), Average Order Total (float), Monthly Average Order Total (float), Most Purchased Product (String) | FTE (1) | DBA | 272 | 0 | 272 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 34 | 272 | 301.4715 | 0.3765% | 0.08832%
| Create Supplier Statistics Table |  |  |  |  | 544 | [11 empty] | 16 | 2 | 34 | 272 | 602.943 | 0.7531% | 0.1766%
R2-6 | Fill Supplier Statistics table with data in fields: Supplier ID (Integer), Supplier Name (String), Products Purchased per Month (Integer), Most Purchased Product (String), Average Sales per Month (Integer) | FTE (1) | DBA | 272 | 0 | 272 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 34 | 272 | 301.4715 | 0.3765% | 0.08832%
R2-7 | Write SQL script to designate primary and foreign keys of new tables in the database | FTE (1) | DBA | 272 | 0 | 272 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 34 | 272 | 301.4715 | 0.3765% | 0.08832%
| Update Server and API Interfaces |  |  | 0 | 0 | 6416 | [11 empty] | 128 | 16 | 50.125 | 401 | 7111.1809 | 8.882% | 2.083%
R2-8 | Create endpoints in server to allow for modification of new database tables | FTE (1) | BED | 464 | 0 | 760 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16 | 2 | 47.5 | 380 | 842.3469 | 1.052% | 0.2468%
R2-9 | Create endpoints in user API interface that allow suppliers to post and remove products from marketplace | FTE (1) | BED | 464 | 0 | 760 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16 | 2 | 47.5 | 380 | 842.3469 | 1.052% | 0.2468%
R2-10 | Create GET endpoints in Medisail API interface to access customer and supplier statistics data | FTE (1) | BED | 464 | 0 | 760 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16 | 2 | 47.5 | 380 | 842.3469 | 1.052% | 0.2468%
R2-11 | Develop functionality for statistics charting in Medisail API interface | FTE (1) | BED | 2320 | 0 | 2912 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 56 | 7 | 52 | 416 | 3227.5185 | 4.031% | 0.9456%
R2-12 | Test endpoints in Postman | FTE (1) | BED | 928 | 0 | 1224 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 24 | 3 | 51 | 408 | 1356.6218 | 1.694% | 0.3974%
| Update User Interfaces |  |  |  |  | 6928 | [11 empty] | 144 | 18 | 48.1111 | 384.8889 | 7678.6567 | 9.591% | 2.25%
| Supplier User Interface |  |  |  |  | 3008 | [11 empty] | 64 | 8 | 47 | 376 | 3333.9202 | 4.164% | 0.9767%
R2-13 | Develop UI components that allow suppliers to post new products to the marketplace | FTE (1) | FED | 1368 | 0 | 2256 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 48 | 6 | 47 | 376 | 2500.4402 | 3.123% | 0.7325%
R2-14 | Test user interface to ensure that components correctly map to API endpoints | FTE (1) | FED | 456 | 0 | 752 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16 | 2 | 47 | 376 | 833.4801 | 1.041% | 0.2442%
| Medisail User Interface |  |  |  |  | 3920 | [11 empty] | 80 | 10 | 49 | 392 | 4344.7364 | 5.427% | 1.273%
R2-15 | Develop UI components that allow Medisail employees to view analytics data rendered from API endpoints connected to new database tables | FTE (1) | FED | 1824 | 0 | 2416 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 48 | 6 | 50.3333 | 402.6667 | 2677.7763 | 3.345% | 0.7845%
R2-16 | Test user interface to ensure that components correct map to API endpoints | FTE (1) | FED | 912 | 0 | 1504 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 32 | 4 | 47 | 376 | 1666.9601 | 2.082% | 0.4884%
| Documentation |  |  |  |  | 2720 | [11 empty] | 40 | 5 | 68 | 544 | 3014.7151 | 3.765% | 0.8832%
R2-17 | Write documentation for integrated system | FTE (2) | SRD, ITM | 2720 | 0 | 2720 | 0 | 20 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 40 | 5 | 68 | 544 | 3014.7151 | 3.765% | 0.8832%
| Test Integrated System |  |  |  |  | 42678 | [11 empty] | 894 | 111.75 | 47.7383 | 381.906 | 47302.2097 | 59.08% | 13.86%
| Unit Testing |  |  |  |  | 13496 | [11 empty] | 304 | 38 | 44.3947 | 355.1579 | 14958.3069 | 18.68% | 4.382%
R2-18 | Write unit tests for new server functionality | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 50 | 400 | 443.3405 | 0.5537% | 0.1299%
R2-19 | Write unit tests for new Medisail API interface endpoints | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.2769% | 0.06494%
R2-20 | Write unit tests for user API interface that ensure that customers don't have access to posting new products | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.2769% | 0.06494%
R2-21 | Write tests for customer user interface | FTE (1) | QAT | 50 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 4 | 0.5 | 25 | 200 | 110.8351 | 0.1384% | 0.03247%
R2-22 | Write tests for supplier user interface marketplace product posting rendering capabilities | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.2769% | 0.06494%
R2-23 | Write tests for Medisail user interface data analytics rendering capabilities | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.5537% | 0.1299%
R2-24 | Write tests for marketplace interface to ensure that new product postings are correctly rendered | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.2769% | 0.06494%
R2-25 | Write tests for shopping cart interface | FTE (1) | QAT | 50 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 4 | 0.5 | 25 | 200 | 110.8351 | 0.1384% | 0.03247%
R2-26 | Conduct back end unit tests | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.5537% | 0.1299%
R2-27 | Conduct user interface tests | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.5537% | 0.1299%
R2-28 | Communicate results of unit tests with development team | FTE (3) | QAT, ITM, SRD | 2576 | 0 | 2976 | 0 | 16 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 16 | 0 | 64 | 8 | 46.5 | 372 | 3298.453 | 4.12% | 0.9663%
R2-29 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 7320 | 0 | 7320 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 15 | 61 | 488 | 8113.1303 | 10.13% | 2.377%
R2-30 | Retest user interfaces | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.2769% | 0.06494%
R2-31 | Reteset back end | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.5537% | 0.1299%
| Integration Testing |  |  |  |  | 13878 | [11 empty] | 294 | 36.75 | 47.2041 | 377.6327 | 15381.697 | 19.21% | 4.506%
R2-32 | Write integration tests between supplier user interface and server | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.2769% | 0.06494%
R2-33 | Write integration tests between Medisail user interface and server | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.2769% | 0.06494%
R2-34 | Write integration tests between marketplace user interface and server | FTE (1) | QAT | 50 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 4 | 0.5 | 25 | 200 | 110.8351 | 0.1384% | 0.03247%
R2-35 | Write integration tests between user API interface and database | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.2769% | 0.06494%
R2-36 | Write integration tests between Medisail API interface and database | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.2769% | 0.06494%
R2-37 | Write mocked integration tests between user interfaces and database | FTE (1) | QAT | 25 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 2 | 0.25 | 25 | 200 | 55.4176 | 0.06922% | 0.01624%
R2-38 | Conduct integration tests between user interfaces and server | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.2769% | 0.06494%
R2-39 | Conduct integration tests between server and database | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.2769% | 0.06494%
R2-40 | Conduct integration tests between user interfaces and database | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.2769% | 0.06494%
R2-41 | Communicate results of integration tests with development team | FTE (3) | QAT, ITM, SRD | 1288 | 0 | 1488 | 0 | 8 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 8 | 0 | 32 | 4 | 46.5 | 372 | 1649.2265 | 2.06% | 0.4832%
R2-42 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 9840 | 0 | 9840 | 0 | 60 | 60 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 20 | 61.5 | 492 | 10906.1752 | 13.62% | 3.195%
R2-43 | Retest integration between user interface and server | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.5537% | 0.1299%
R2-44 | Retest integration between server and database | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.5537% | 0.1299%
R2-45 | Retest integration between user interface and database | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.2769% | 0.06494%
| System Testing |  |  |  |  | 15304 | [11 empty] | 296 | 37 | 51.7027 | 413.6216 | 16962.2058 | 21.19% | 4.969%
R2-46 | Write system tests of the entire integrated system | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.5537% | 0.1299%
R2-47 | Conduct system tests of the integrated system | FTE (3) | QAT, SRD, PM | 400 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0 | 32 | 4 | 25 | 200 | 886.6809 | 1.107% | 0.2598%
R2-48 | Communicate results of system tests with development teams | FTE (3) | QAT, SRD, PM | 744 | 544 | 1488 | 8 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 32 | 4 | 46.5 | 372 | 1649.2265 | 2.06% | 0.4832%
R2-49 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 9840 | 0 | 9840 | 0 | 60 | 60 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 20 | 61.5 | 492 | 10906.1752 | 13.62% | 3.195%
R2-50 | Reconduct system tests | FTE (3) | QAT, SRD, PM | 1388 | 1088 | 2776 | 16 | 16 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 0 | 56 | 7 | 49.5714 | 396.5714 | 3076.7828 | 3.843% | 0.9014%
| Deploy Release 2 |  |  |  |  | 9323 | [11 empty] | 141 | 17.625 | 66.1206 | 528.9645 | 10333.1576 | 12.91% | 3.027%
| Conduct Required Trainings |  |  |  |  | 3728 | [11 empty] | 56 | 7 | 66.5714 | 532.5714 | 4131.933 | 5.161% | 1.211%
R2-51 | Update sales manager on new capabilities of integrated e-procurement system | FTE (2) | PM, SM | 1008 | 1088 | 2096 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 32 | 4 | 65.5 | 524 | 2323.104 | 2.902% | 0.6806%
R2-52 | Train Medisail non-technical employees on integrated e-procurement system analytics capabilities | FTE (1) | PM | 0 | 1632 | 1632 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 3 | 68 | 544 | 1808.8291 | 2.259% | 0.5299%
| Pre-Deployment Marketing |  |  |  |  | 504 | [11 empty] | 8 | 1 | 63 | 504 | 558.609 | 0.6977% | 0.1637%
R2-53 | Create advertisement materials for integrated product | FTE (1) | SM | 504 | 0 | 504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 1 | 63 | 504 | 558.609 | 0.6977% | 0.1637%
| Product Deployment |  |  | 0 | 0 | 3264 | [11 empty] | 48 | 6 | 68 | 544 | 3617.6581 | 4.519% | 1.06%
R2-54 | Deploy integrated system | FTE (1) | SRD | 544 | 0 | 544 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 68 | 544 | 602.943 | 0.7531% | 0.1766%
R2-55 | Monitor system performance after deployment | FTE (1) | SRD | 2720 | 0 | 2720 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 5 | 68 | 544 | 3014.7151 | 3.765% | 0.8832%
| Collect Supplier Feedback on Analytics Capabilities |  |  |  |  | 1827 | [11 empty] | 29 | 3.625 | 63 | 504 | 2024.9575 | 2.529% | 0.5932%
R2-56 | Create Medisail non-technical employee survey about new analytics capabilities | FTE (1) | SM | 126 | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0.25 | 63 | 504 | 139.6522 | 0.1744% | 0.04091%
R2-57 | Create new customer survey with refined prompts based on results of Release 1 survey | FTE (1) | SM | 126 | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0.25 | 63 | 504 | 139.6522 | 0.1744% | 0.04091%
R2-58 | Send survey to Medisail non-technical employees who use the system | FTE (1) | SM | 252 | 0 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0.5 | 63 | 504 | 279.3045 | 0.3489% | 0.08183%
R2-59 | Send revised survey to customers | FTE (1) | SM | 63 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0.125 | 63 | 504 | 69.8261 | 0.08722% | 0.02046%
R2-60 | Collect and analyze feedback | FTE (1) | SM | 1008 | 0 | 1008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 2 | 63 | 504 | 1117.2179 | 1.395% | 0.3273%
R2-61 | Share survey feedback with team | FTE (1) | SM | 252 | 0 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0.5 | 63 | 504 | 279.3045 | 0.3489% | 0.08183%
| Release 3: Advanced System |  |  |  |  | 107408 | [11 empty] | 2236 | 279.5 | 48.0358 | 384.2862 | 119045.7787 | 100% | 34.88%
| Adjust Plan Based on Supplier Feedback |  |  |  |  | 2176 | [11 empty] | 32 | 4 | 68 | 544 | 2411.7721 | 2.026% | 0.7066%
R3-1 | Determine which aspects of feedback are relevant | FTE (2) | PM, SRD | 544 | 544 | 1088 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2 | 68 | 544 | 1205.886 | 1.013% | 0.3533%
R3-2 | Revise Release 3 requirements based on feedback assessment | FTE (2) | PM, SRD | 544 | 544 | 1088 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2 | 68 | 544 | 1205.886 | 1.013% | 0.3533%
| Update Backend for Advanced Analytics |  |  |  |  | 15096 | [11 empty] | 320 | 40 | 47.175 | 377.4 | 16731.6687 | 14.05% | 4.902%
| User API Interface |  |  |  |  | 3896 | [11 empty] | 92 | 11.5 | 42.3478 | 338.7826 | 4318.136 | 3.627% | 1.265%
R3-3 | Write SQL queries to query analytics data from database for suppliers | FTE (1) | DBA | 544 | 0 | 544 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2 | 34 | 272 | 602.943 | 0.5065% | 0.1766%
R3-4 | Write SQL queries to query analytics data from database for customers | FTE (1) | DBA | 544 | 0 | 544 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2 | 34 | 272 | 602.943 | 0.5065% | 0.1766%
R3-5 | Create endpoints for analytics data for supplier UI | FTE (1) | BED | 464 | 0 | 612 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 12 | 1.5 | 51 | 408 | 678.3109 | 0.5698% | 0.1987%
R3-6 | Create endpoints for analytics data for user UI | FTE (1) | BED | 464 | 0 | 612 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 12 | 1.5 | 51 | 408 | 678.3109 | 0.5698% | 0.1987%
R3-7 | Test endpoints to ensure that supplier and user analytics data is mapped correctly | FTE (1) | BED | 696 | 0 | 1584 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 36 | 4.5 | 44 | 352 | 1755.6282 | 1.475% | 0.5143%
| Tableau Functionality |  |  |  |  | 11200 | [11 empty] | 228 | 28.5 | 49.1228 | 392.9825 | 12413.5327 | 10.43% | 3.637%
R3-8 | Negotiate and obtain Tableau licence | FTE (1) | PM | 0 | 2720 | 2720 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 5 | 68 | 544 | 3014.7151 | 2.532% | 0.8832%
R3-9 | Review Tableau documentation | FTE (2) | DBA, BED | 2208 | 0 | 2208 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 6 | 46 | 368 | 2447.2393 | 2.056% | 0.717%
R3-10 | Refine database tables as needed per Tableau documentation | FTE (1) | DBA | 1088 | 0 | 1088 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 4 | 34 | 272 | 1205.886 | 1.013% | 0.3533%
R3-11 | Create Tableau-specific API endpoints for suppliers | FTE (1) | BED | 696 | 0 | 992 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 20 | 2.5 | 49.6 | 396.8 | 1099.4843 | 0.9236% | 0.3221%
R3-12 | Create Tableau-specific API endpoints for customers | FTE (1) | BED | 696 | 0 | 992 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 20 | 2.5 | 49.6 | 396.8 | 1099.4843 | 0.9236% | 0.3221%
R3-13 | Create Tableau-specific API endpoints for Medisail non-technical employees | FTE (1) | BED | 696 | 0 | 992 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 20 | 2.5 | 49.6 | 396.8 | 1099.4843 | 0.9236% | 0.3221%
R3-14 | Test all Tableau endpoints | FTE (2) | DBA, BED | 2208 | 0 | 2208 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 6 | 46 | 368 | 2447.2393 | 2.056% | 0.717%
| Update Frontend for Advanced Analytics |  |  |  |  | 19392 | [11 empty] | 332 | 41.5 | 58.4096 | 467.2771 | 21493.1452 | 18.05% | 6.297%
R3-15 | Create UI components in customer user interface to render analytics data from database | FTE (1) | FED | 2280 | 0 | 2872 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 56 | 7 | 51.2857 | 410.2857 | 3183.1845 | 2.674% | 0.9326%
R3-16 | Create UI components in customer user interface to render Tableau graphics and charts | FTE (2) | FED, SRD | 3000 | 0 | 3000 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 6 | 62.5 | 500 | 3325.0534 | 2.793% | 0.9741%
R3-17 | Create UI components in supplier user interface to render analytics data from database | FTE (1) | FED | 2280 | 0 | 3020 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 60 | 7.5 | 50.3333 | 402.6667 | 3347.2204 | 2.812% | 0.9806%
R3-18 | Create UI components in supplier user interface to render Tableau graphics and charts | FTE (2) | FED, SRD | 3000 | 0 | 3000 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 6 | 62.5 | 500 | 3325.0534 | 2.793% | 0.9741%
R3-19 | Create UI components in Medisail user interface to render Tableau graphics and charts | FTE (2) | FED, SRD | 3000 | 0 | 3000 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 6 | 62.5 | 500 | 3325.0534 | 2.793% | 0.9741%
R3-20 | Test database analytics rendering in customer and supplier user interfaces | FTE (2) | FED, SRD | 2000 | 0 | 2000 | 0 | 16 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 4 | 62.5 | 500 | 2216.7023 | 1.862% | 0.6494%
R3-21 | Test Tableau integration in all user interfaces | FTE (2) | FED, SRD | 2500 | 0 | 2500 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 5 | 62.5 | 500 | 2770.8778 | 2.328% | 0.8118%
| Documentation |  |  |  |  | 5440 | [11 empty] | 80 | 10 | 68 | 544 | 6029.4302 | 5.065% | 1.766%
R3-22 | Write documentation for advanced system | FTE (2) | SRD, ITM | 5440 | 0 | 5440 | 0 | 40 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 80 | 10 | 68 | 544 | 6029.4302 | 5.065% | 1.766%
| Test Advanced System |  |  |  |  | 55368 | [11 empty] | 1320 | 165 | 41.9455 | 335.5636 | 61367.1856 | 51.55% | 17.98%
| Unit Testing |  |  |  |  | 16584 | [11 empty] | 456 | 57 | 36.3684 | 290.9474 | 18380.8952 | 15.44% | 5.385%
R3-23 | Write unit tests for data analytics API endpoints to ensure that only applicable data is accessible | FTE (1) | QAT | 150 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6 | 0 | 12 | 1.5 | 25 | 200 | 332.5053 | 0.2793% | 0.09741%
R3-24 | Write unit tests for Tableau API endpoints | FTE (1) | QAT | 150 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6 | 0 | 12 | 1.5 | 25 | 200 | 332.5053 | 0.2793% | 0.09741%
R3-25 | Write unit tests for new Medisail API interface endpoints to ensure that all data analytics is accessable | FTE (1) | QAT | 150 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6 | 0 | 12 | 1.5 | 25 | 200 | 332.5053 | 0.2793% | 0.09741%
R3-26 | Write tests for customer user interface data analytics capabilities | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.1862% | 0.06494%
R3-27 | Write tests for supplier user interface data analytics capabilities | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.1862% | 0.06494%
R3-28 | Write tests for Medisail user interface data analytics rendering capabilities | FTE (1) | QAT | 250 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10 | 0 | 20 | 2.5 | 25 | 200 | 554.1756 | 0.4655% | 0.1624%
R3-29 | Write tests for Tableau integration in customer user interface | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.3724% | 0.1299%
R3-30 | Write tests for Tableau integration in supplier user interface | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.3724% | 0.1299%
R3-31 | Write tests for Tableau integration in Medisail user interface | FTE (1) | QAT | 400 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0 | 32 | 4 | 25 | 200 | 886.6809 | 0.7448% | 0.2598%
R3-32 | Conduct back end unit tests | FTE (1) | QAT | 800 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 64 | 8 | 25 | 200 | 1773.3618 | 1.49% | 0.5195%
R3-33 | Conduct user interface tests | FTE (1) | QAT | 600 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 48 | 6 | 25 | 200 | 1330.0214 | 1.117% | 0.3897%
R3-34 | Communicate results of unit tests with development team | FTE (3) | QAT, ITM, SRD | 1664 | 0 | 1864 | 0 | 8 | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 40 | 5 | 46.6 | 372.8 | 2065.9665 | 1.735% | 0.6053%
R3-35 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 7320 | 0 | 7320 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 15 | 61 | 488 | 8113.1303 | 6.815% | 2.377%
R3-36 | Retest user interfaces | FTE (1) | QAT | 300 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 0 | 24 | 3 | 25 | 200 | 665.0107 | 0.5586% | 0.1948%
R3-37 | Reteset back end | FTE (1) | QAT | 300 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 0 | 24 | 3 | 25 | 200 | 665.0107 | 0.5586% | 0.1948%
| Integration Testing |  |  |  |  | 17568 | [11 empty] | 416 | 52 | 42.2308 | 337.8462 | 19471.5127 | 16.36% | 5.705%
R3-38 | Write integration tests between supplier user interface and server | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.3724% | 0.1299%
R3-39 | Write integration tests between Medisail user interface and server | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.3724% | 0.1299%
R3-40 | Write integration tests between marketplace user interface and server | FTE (1) | QAT | 200 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 16 | 2 | 25 | 200 | 443.3405 | 0.3724% | 0.1299%
R3-41 | Write integration tests between user API interface and database | FTE (1) | QAT | 300 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 0 | 24 | 3 | 25 | 200 | 665.0107 | 0.5586% | 0.1948%
R3-42 | Write integration tests between Medisail API interface and database | FTE (1) | QAT | 300 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 0 | 24 | 3 | 25 | 200 | 665.0107 | 0.5586% | 0.1948%
R3-43 | Write mocked integration tests between user interfaces and database | FTE (1) | QAT | 150 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6 | 0 | 12 | 1.5 | 25 | 200 | 332.5053 | 0.2793% | 0.09741%
R3-44 | Conduct integration tests between user interfaces and server | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.1862% | 0.06494%
R3-45 | Conduct integration tests between server and database | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.1862% | 0.06494%
R3-46 | Conduct integration tests between user interfaces and database | FTE (1) | QAT | 100 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 8 | 1 | 25 | 200 | 221.6702 | 0.1862% | 0.06494%
R3-47 | Communicate results of integration tests with development team | FTE (3) | QAT, ITM, SRD | 1288 | 0 | 1488 | 0 | 8 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 8 | 0 | 32 | 4 | 46.5 | 372 | 1649.2265 | 1.385% | 0.4832%
R3-48 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 10980 | 0 | 10980 | 0 | 60 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 22.5 | 61 | 488 | 12169.6955 | 10.22% | 3.565%
R3-49 | Retest integration between user interface and server | FTE (1) | QAT | 300 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 0 | 24 | 3 | 25 | 200 | 665.0107 | 0.5586% | 0.1948%
R3-50 | Retest integration between server and database | FTE (1) | QAT | 300 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 0 | 24 | 3 | 25 | 200 | 665.0107 | 0.5586% | 0.1948%
R3-51 | Retest integration between user interface and database | FTE (1) | QAT | 300 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 0 | 24 | 3 | 25 | 200 | 665.0107 | 0.5586% | 0.1948%
| System Testing |  |  |  |  | 21216 | [11 empty] | 448 | 56 | 47.3571 | 378.8571 | 23514.7777 | 19.75% | 6.889%
R3-52 | Write system tests of the entire advanced system | FTE (1) | QAT | 600 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 48 | 6 | 25 | 200 | 1330.0214 | 1.117% | 0.3897%
R3-53 | Conduct system tests of the advanced system | FTE (3) | QAT, SRD, PM | 400 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0 | 32 | 4 | 25 | 200 | 886.6809 | 0.7448% | 0.2598%
R3-54 | Communicate results of system tests with development teams | FTE (3) | QAT, SRD, PM | 1488 | 1088 | 2976 | 16 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0 | 64 | 8 | 46.5 | 372 | 3298.453 | 2.771% | 0.9663%
R3-55 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 14640 | 0 | 14640 | 0 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 30 | 61 | 488 | 16226.2606 | 13.63% | 4.754%
R3-56 | Reconduct system tests | FTE (3) | QAT, SRD, PM | 800 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 64 | 8 | 25 | 200 | 1773.3618 | 1.49% | 0.5195%
| Deploy Release 3 |  |  |  |  | 9936 | [11 empty] | 152 | 19 | 65.3684 | 522.9474 | 11012.5769 | 9.251% | 3.226%
| Conduct Required Trainings |  |  |  |  | 5664 | [11 empty] | 88 | 11 | 64.3636 | 514.9091 | 6277.7008 | 5.273% | 1.839%
R3-57 | Update sales manager on new capabilities of advanced e-procurement system | FTE (2) | PM, SM | 1512 | 1632 | 3144 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 48 | 6 | 65.5 | 524 | 3484.656 | 2.927% | 1.021%
R3-58 | Train Medisail non-technical employees on new analytics capabilities | FTE (1) | PM | 1008 | 0 | 1008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 2 | 63 | 504 | 1117.2179 | 0.9385% | 0.3273%
R3-59 | Train customers on new analytics capabilities | FTE (1) | PM | 756 | 0 | 756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 1.5 | 63 | 504 | 837.9135 | 0.7039% | 0.2455%
R3-60 | Train suppliers on new analytics capabilities | FTE (1) | PM | 756 | 0 | 756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 1.5 | 63 | 504 | 837.9135 | 0.7039% | 0.2455%
| Pre-Deployment Marketing |  |  |  |  | 1008 | [11 empty] | 16 | 2 | 63 | 504 | 1117.2179 | 0.9385% | 0.3273%
R3-61 | Create advertisement materials for advanced product | FTE (1) | SM | 504 | 0 | 504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 1 | 63 | 504 | 558.609 | 0.4692% | 0.1637%
R3-62 | Conduct sales calls with potential new customers | FTE (1) | SM | 504 | 0 | 504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 1 | 63 | 504 | 558.609 | 0.4692% | 0.1637%
| Product Deployment |  |  | 0 | 0 | 3264 | [11 empty] | 48 | 6 | 68 | 544 | 3617.6581 | 3.039% | 1.06%
R3-63 | Deploy advanced system | FTE (1) | SRD | 544 | 0 | 544 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 68 | 544 | 602.943 | 0.5065% | 0.1766%
R3-64 | Monitor system performance after deployment | FTE (1) | SRD | 2720 | 0 | 2720 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 5 | 68 | 544 | 3014.7151 | 2.532% | 0.8832%
| End of Project Activities |  |  |  |  | 20560 | [11 empty] | 340 | 42.5 | 60.4706 | 483.7647 | 22787.6993 | 100% | 6.676%
| Product Adoption |  |  |  |  | 6818 | [11 empty] | 106 | 13.25 | 64.3208 | 514.566 | 7556.738 | 33.16% | 2.214%
EOP-1 | Plan product education workshops for customers and suppliers | FTE (2) | PM, SM | 756 | 816 | 1572 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 24 | 3 | 65.5 | 524 | 1742.328 | 7.646% | 0.5104%
EOP-2 | Schedule product education workshops | FTE (1) | SM | 126 | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0.25 | 63 | 504 | 139.6522 | 0.6128% | 0.04091%
EOP-3 | Conduct product education workshops | FTE (1) | SM | 2520 | 0 | 2520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 40 | 5 | 63 | 504 | 2793.0449 | 12.26% | 0.8183%
EOP-4 | Gather feedback from customers and suppliers during workshops | FTE (1) | SM | 504 | 0 | 504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 1 | 63 | 504 | 558.609 | 2.451% | 0.1637%
EOP-5 | Train Medisail sales teams and customer support on product | FTE (2) | PM, SM | 1008 | 1088 | 2096 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 32 | 4 | 65.5 | 524 | 2323.104 | 10.19% | 0.6806%
| Continuous Improvement |  |  |  |  | 13742 | [11 empty] | 234 | 29.25 | 58.7265 | 469.812 | 15230.9613 | 66.84% | 4.462%
EOP-6 | Send monthly surveys to customers and suppliers | FTE (1) | SM | 126 | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0.25 | 63 | 504 | 139.6522 | 0.6128% | 0.04091%
EOP-7 | Gather feedback from surveys | FTE (1) | SM | 504 | 0 | 504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 1 | 63 | 504 | 558.609 | 2.451% | 0.1637%
EOP-8 | Discuss results of surveys | FTE (2) | PM, SM | 504 | 544 | 1048 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 16 | 2 | 65.5 | 524 | 1161.552 | 5.097% | 0.3403%
EOP-9 | Determine feasibility of improvements suggested in survey results | FTE (3) | PM, SRD, ITM | 2176 | 1088 | 3264 | 16 | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 48 | 6 | 68 | 544 | 3617.6581 | 15.88% | 1.06%
EOP-10 | Implement accepted improvements to software system | FTE (3) | SRD, BED, FED | 7320 | 0 | 8800 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 160 | 20 | 55 | 440 | 9753.49 | 42.8% | 2.857%
Total |  | Totals |  | 237476 | 31212 | 307967 | 459 | 1117 | 826 | 918 | 253 | 806 | 169 | 334 | 0 | 798 | 517 | 6197 | 774.625 | 53.6289 | 429.0316 | 341335.574 | - | 100%
Summary of Project Software Costs |  |  | MATCH THIS ^ |  |  | Development Cost | [11 empty] | Duration (Hours) | Duration (Days) | Average Hourly Rate | Average Daily Rate | Development Cost with Overhead | % Total Cost of Project
Phase 1: Pre-Development Activities | [5 empty] | 10424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 171 | 21.375 | 60.9591 | 487.6725 | 11553.4522 | 3.385%
Phase 2: Release 1 | [5 empty] | 97340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2018 | 252.25 | 48.2359 | 385.887 | 107886.8995 | 31.61%
Phase 3: Release 2 | [5 empty] | 72235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1432 | 179 | 50.4434 | 403.5475 | 80061.7442 | 23.46%
Phase 4: Release 3 | [5 empty] | 107408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2236 | 279.5 | 48.0358 | 384.2862 | 119045.7787 | 34.88%
Phase 5: End of Project Activities | [5 empty] | 20560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 340 | 42.5 | 60.4706 | 483.7647 | 22787.6993 | 6.676%
Non-Development Phases 1 and 5 | [5 empty] | 30984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 511 | 63.875 | 60.7148 | 485.7186 | 34341.1516 | 10.06%
Release Phases 2-4 | [5 empty] | 276983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 5686 | 710.75 | 48.905 | 391.2402 | 306994.4224 | 89.94%
Total of Project | [5 empty] | 307967 | 459 | 1117 | 826 | 918 | 253 | 806 | 169 | 334 | 0 |  |  | 6197 | 774.625 | 53.6289 | 429.0316 | 341335.574 | 100%
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I've locked the spreadsheet to prevent accidental changes because there are a lot of formulas and the sheets all link together. If anyone wants to make a change, please let me know

## Business Benefits
Business Benefits | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Increased company revenue from e-procurement product | 0 | 960000 | 1056000 | 1161600 | 1277760 | 1405536 | 5860896
Benefits of increased visibility of the Medisail brand due to e-procurement product that benefits other operating areas of the company | 0 | 5000 | 5250 | 5512.5 | 5788.125 | 6077.5312 | 27628.1562
Increased revenue from subscription tier upgrades | 0 | 0 | 54600 | 57330 | 60196.5 | 63206.325 | 235332.825
Total Value of Business Benefits | 0 | 965000 | 1115850 | 1224442.5 | 1343744.625 | 1474819.8562 | 6123856.9813
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I've locked the spreadsheet to prevent accidental changes because there are a lot of formulas and the sheets all link together. If anyone wants to make a change, please let me know

## Financial Feasibility Analysis
| Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Cost/Benefit Analysis
Project Benefits
Benefits from Developing e-Procurement System | 0 | 965000 | 1115850 | 1224442.5 | 1343744.625 | 1474819.8562 | 6123856.9813
Project Costs
Project Software Development Costs | 341335.574 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost of Ownership - Rollout | 595225 | 574006.2133 | 589046.2133 | 613707.0133 | 628083.4293 | 644756.5257 | 3644824.395
Total Costs | 936560.574 | 574006.2133 | 589046.2133 | 613707.0133 | 628083.4293 | 644756.5257 | 3986159.969
Project Cash Flows
Annual Cashflow | -936560.574 | 390993.7867 | 526803.7867 | 610735.4867 | 715661.1957 | 830063.3306 | 2137697.0123
Cummulative Cashflow | -936560.574 | -545566.7873 | -18763.0006 | 591972.486 | 1307633.6817 | 2137697.0123 | 2137697.0123
Return on Investment Analysis
Return on Investment (ratio) | -100% | 68.12% | 89.43% | 99.52% | 113.9% | 128.7% | 53.63%
Payback period (in years) | 2.0307
Net Present Value Analysis
Risk Free Rate (10 year Treasury on 11/17/23) | 4.44%
Risk Premium | 20%
Discount Rate | 24.44%
Present Value
Present Value per Year | -936560.574 | 314202.6572 | 340195.7495 | 316937.1498 | 298447.1665 | 278170.5931 | 611392.7421
Net Present Value | 611392.7421
Internal Rate of Return | 49.37%
IRR NPV Calculation | -936560.574 | 261764.9256 | 236119.6247 | 183264.3327 | 143771.8504 | 111639.8436 | 0.0029891
Highest Acceptable Risk Premium | 44.93%
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I've locked the spreadsheet to prevent accidental changes because there are a lot of formulas and the sheets all link together. If anyone wants to make a change, please let me know

## Resources
Category | Resource | Description | Abbr. | Rate (hourly unless otherwise noted) | Daily Rate (if applicable) | Source | Type
Labor | Project Manager | Responsible for organizing and planning the e-procurement software system project. Communicates with stakeholders and development team and defines project goals, MOV, and keeps project on track. | PM | 68 | 544 | Salary.com | FTE
| Senior Developer | Leads and oversees development team and assists with all aspects of development. | SRD | 68 | 544 | Salary.com | FTE
| Backend Developer | Responsible for developing the backend components of the application including the server and API interfaces. Responsible for integrating backend components with frontend componenets and backend components with the databases. | BED | 58 | 464 | Salary.com | FTE
| Frontend Developer | Responsible for developing the frontend components of the application including the customer UI, supplier UI, Medisail UI, and marketplace UI. Responsible for integrating frontend components with backend components. | FED | 57 | 456 | Salary.com | FTE
| Database Administrator | Responsible for creating and maintaining the databases. | DBA | 34 | 272 | Salary.com | FTE
| QA Tester 1 | Responsible for creating and implementing unit, integration, and system tests. Communicates with the IT Manager and Senior Developer about results of test cases. | QAT1 | 25 | 200 | Salary.com | FTE
| IT Manager | Oversees the development team and acts as a liason between the development team and the Project Manager. | ITM | 68 | 544 | Salary.com | FTE
| Sales Manager | Responsible for overseeing introduction of e-procurement product to customers. Communicates with Project Manager about capabilities of the system and limitations at each deployment phase. | SM | 63 | 504 | Salary.com | FTE
| QA Tester 2 | Responsible for creating and implementing unit, integration, and system tests. Communicates with the IT Manager and Senior Developer about results of test cases. | QAT2 | 25 | 200 | Salary.com | FTE
| Junior Developer | Assists the Frontend and Backend Developers in their development tasks | JD | 37 | 296 | Salary.com | FTE
| System Administrator | Responsible for managing, updating, and patching our infrastructure system. | SA | 53 | 424 | Salary.com | FTE
| Technical Support Specialist | Responsible for answering customer questions and troubleshooting customer issues with product | TS | 26 | 208 | Zippia | FTE
Licenses | Tableau License | License for use of Tableau in software system |  | $42 per month |  | Tableau | License
| Oracle DBMS License | License for use of Oracle DBMS in software system |  | $950 per year year |  | Oracle | License
Contracts | Data/Server Center | Yearly fee to rent data center capabilities (4 CPUs, 128 GB RAM, 100 TB of standard storage, and 2 TB of high-tier storage) |  | $204,204 per year |  | UC Santa Cruz | Rental
| Total Cost of Distribution Contracts | Medisail's new contracts with distribution companies to distribute products to customers |  | 7% of annual revenue |  | Bain Consulting | Contract
Revenue | Tier 1 Subscription Fee | Monthly fee for customers of Medisail who purchase Tier 1 access to the e-procurement system |  | $8 per month |  |  | Revenue
| Tier 2 Subscription Fee | Monthly fee for customers of Medisail who purchase Tier 2 access to the e-procurement system |  | $12 per month |  |  | Revenue
| Tier 3 Subscription Fee | Monthly fee for customers of Medisail who purchase Tier 3 access to the e-procurement system |  | $30 per month |  |  | Revenue