## High-Level WBS
Task Number | Task Name
Pre-Development Activities
PDA-1 | Gather requirements
PDA-2 | Ensure system software is up to date
PDA-3 | Install IDEs and required third party technologies
PDA-4 | Gather human resources
Release 1: Basic (Core) System
Develop Basic System Components
Basic Components of Backend
R1-1 | Create database tables for sales, orders, inventory reporting, and statistics
R1-2 | Develop basic Medisail API interface
R1-3 | Develop basic user API interface
Basic Components of Frontend
R1-4 | Develop basic marketplace
R1-5 | Develop basic customer user interface
R1-6 | Develop basic supplier user interface
R1-7 | Develop basic Medisail user interface
Documentation
R1-8 | Create documentation for Release 1
Testing
R1-9 | Create and conduct unit, system, and integration tests
Deployment
R1-10 | Deploy Release 1 and collect feedback on deployment
Release 2: Integrated System
Modify System Components
Modify Components of Backend
R2-1 | Develop customer statistics and order tables in database
R2-2 | Update user API interface to interact with new tables
R2-3 | Update Medisail API interface to interact with new tables
Modify Components of Frontend
R2-4 | Update interface to allow for posting of medical goods
R2-5 | Develop UI components to allow for data analytics
Documentation
R2-6 | Create documentation for Release 2
Testing
R2-7 | Create and conduct unit, system, and integration tests
Deployment
R2-8 | Deploy Release 2 and collect feedback on deployment
Release 3: Advanced System
Modify System Components
Modify/Maintain Components of Backend
R3-1 | Update API to allow suppliers and customers to collect data and perform analytics on orders
R3-2 | SQL maintenance operations e.g. Check database integrity
Modify Components of Frontend
R3-3 | Develop data rendering capabilities for customers and suppliers
R3-4 | Test data rendering capabilities
Tableau Integration
R3-5 | Update tables, endpoints, and user interfaces to integrate Tableau graphical analysis
Documentation
R3-6 | Create documentation for Release 3
Testing
R3-7 | Create and conduct unit, system, and integration tests
Deployment
R3-8 | Deploy Release 3 and collect feedback on deployment
End of Project Activities
Product Adoption
EOP-1 | Conduct product education workshops
EOP-2 | Train Medisail sales teams and customer support on product
Continuous Improvement
EOP-3 | Create and send monthly feedback surveys to customers and suppliers
EOP-4 | Implement feasible improvements from analyzed survey results
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: do we want to add something for hardware infrastructure, like server (or cloud server) setup

## Mid-Level WBS
Task Number | Task Name
Pre-Development Activities
Install & configure development environment
PDA-1 | Purchase hardware needed for enviroment
PDA-2 | Conduct system upgrades for enviroment
PDA-3 | Setup new accounts needed to maintain the development enviroment
PDA-4 | Identify stakeholders & gather requirements
PDA-5 | Begin to gather human resources
Release 1: Basic (Core) System
Database Creation
R1-1 | Develop table schema for medical supplies inventory
R1-2 | Develop table schema for suppliers
R1-3 | Develop table schema for distrubutors
R1-4 | Develop table schema for Customers & purchase history
API Creation
R1-5 | Develop RESTful API
R1-6 | Develop Server
R1-7 | Create API user endpoint for user interfaces
R1-8 | Create API user endpoint for MediSail interface
R1-9 | Develop SQL script to accomplish general queries from inventory database
Creating User Interfaces
R1-10 | Develop interface for all user catagories (customers, suppliers, and Medisail non-technical employees)
R1-11 | Devlop interface for Shopping Cart & Checkout
R1-12 | Develop Interface for Login interface
Documentation
R1-13 | Write documentation for Release 1
Test Core System
Unit Testing
R1-14 | Write and conduct tests for Customer user interface
R1-15 | Write and conduct tests for Supplier user interface
R1-16 | Write and conduct tests for Medisail employee user interface
R1-17 | Write and conduct tests for shopping cart and checkout interface
R1-18 | Write and conduct unit tests for API endpoints
R1-19 | Write and conduct tests for server
Integration Testing
R1-19 | Write and conduct tests for user interfaces and server integration
R1-20 | Write and conduct tests for database and server integration
R1-21 | Write and conduct mocked tests for user interfaces and database integration
Core Functionality System Testing
R1-21 | Write tests for core system functionality
R1-22 | Modify & Retest core system functionality based on results
Deployment
E-Procurement System Training
R1-23 | Plan and conduct sales management training
R1-24 | Plan and conduct training for Medisail non-technical employees
Pre-Deployment Marketing
R1-25 | Create and deploy advertizements for core sytem
R1-26 | Identify unique pilot customers
Product Deployment
R1-27 | Deploy Core System
R1-28 | Monitor overall performance
Collect & Analyze Feedback
R1-29 | Create and send customer surveys
R1-30 | Collect and analyze customer feedback
Release 2: Integrated System
Handle Customer Feedback
R2-1 | Restructure system requirements based on customer feedback
R2-2 | Refine initial customer survey's questions and prompts
Database Functionality
R2-3 | Develop customer statistics table schema for database
R2-4 | Develop supplier statistics table schema for database
R2-5 | Develop SQL scripts for quering inventory
API Updates
End Point Updates
R2-6 | Update endpoints in server for new database tables
R2-7 | Update endpoints for supplier interface
R2-8 | Update endpoints for Medisail interface
R2-9 | Employ Postman to test endpoints
Update User Interfaces
Supplier User Interface
R2-10 | Update interface to allow for posting of medical supplies
Medisail User Interface
R2-11 | Develop UI components to allow for data analytics
Documentation
R2-12 | Write documentation for Release 2
Test Integrated System
Unit Testing
R2-13 | Write and conduct tests for new server functionality
R2-14 | Write and conduct tests for all new interface API endpoints
R2-15 | Write and conduct tests for new user interface functionality
R2-16 | Modify system based on test results
Integration Testing
R2-17 | Write integration tests for user interfaces and server
R2-18 | Write integration tests for API interfaces and database
R2-19 | Conduct integration tests and modify system based on test results
R2-20 | System Testing
R2-21 | Write system tests of the entire integrated system
R2-22 | Conduct system tests of the integrated system and modify system based on results
Deploy Release 2
Conduct Required Trainings
R2-23 | Retrain MediSail employees on new anlytics features
Pre-Deployment Marketing
R2-24 | Create advertisement materials for integrated analytics features
Product Deployment
Deploy integrated system
Collect Supplier Feedback on Analytics Capabilities
R2-25 | Create surveys on new capabilities and system performance
R2-26 | Collect and analyze feedback
Release 3: Advanced System
Adjust Plan Based on Supplier Feedback
R3-1 | Revise sytem requirements based on feedback assessment
Update Backend for Advanced Analytics
User API Interface
R3-2 | Write SQL queries for invetory management
R3-3 | Create API endpoints for user interfaces to perform analytics
Tableau Functionality
R3-4 | Obtain Tableau license
R3-5 | Create Tableau-specific API endpoints for user interfaces
R3-6 | Test all Tableau endpoints
Update Frontend for Advanced Analytics
R3-7 | Create UI components for user interfaces to render analytics data from database
R3-8 | Create UI components for user interfaces to render Tableau graphics and charts
R3-9 | Test database analytics rendering and integration
Documentation
R3-10 | Write documentation for advanced system
Test Advanced System
Unit Testing
R3-11 | Write unit tests for Data analytics API end points
R3-12 | Write unit tests for new user interfaces data analytics capablilities
R3-13 | Write tests for Tableau integration for user interfaces
R3-14 | Conduct unit tests and modify system based on test results
Integration Testing
R3-15 | Write integration tests between user interfaces and server
R3-16 | Write integration tests for API interfaces and database
R3-17 | Conduct integration tests and modify system based on test results
System Testing
R3-18 | Write system tests of the entire advanced system
R3-19 | Conduct system tests of the integrated system and modify system based on results
Deploy Release 3
Conduct Required Trainings
R3-20 | Retrain MediSail employees on analytics and new tableu features
Pre-Deployment Marketing
R3-21 | Create advertisement materials for existing analytics and new tableu features
Product Deployment
R3-22 | Deploy advanced system
End of Project Activities
Product Adoption
EOP-1 | Conduct product education workshops
EOP-2 | Train Medisail sales teams and customer support on product
Continuous Improvement
EOP-3 | Send monthly surveys to customers and suppliers
EOP-4 | Analyze results of surverys
EOP-5 | Implement feasible improvements from analyzed survey results
Note on B3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These don't seem to link to the high level WBS. shouldn't they?
Note on A4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I don't think we should copy the format from the high level since it makes it hard to trace (and place into project in the correct location). instead I would call these PDA-1.x where x are the children of the parent high level wbs task PDA-1.

## Low-Level WBS
Task Number | Task Name
Pre-Development Activities
Requirements Analysis
PDA-1 | Gather requirements from stakeholders
PDA-2 | Create software system requirements analysis
PDA-3 | Receive approval of requirements analysis
Feasibility Study
PDA-4 | Conduct cash flow analysis
PDA-5 | Conduct risk assessment
Development Environment Setup
PDA-5 | Update laptops to Windows 11 OS
PDA-6 | Install and configure Visual Studio Code
PDA-7 | Install and configure Postman, Maven, and Junit 5 testing software
PDA-8 | Install and configure PostgreSQL and SQL interface
Release 1: Basic (Core) System
Mock Up User Interfaces
R1-1 | Mock up user interface for Medisail customers
R1-2 | Mock up user interface for suppliers
R1-3 | Mock up user interface for Medisail non-technical employees
R1-4 | Mock up marketplace user interface
R1-5 | Mock up shopping cart and checkout interfaces
R1-6 | Mock up login portal user interface
Database Creation
R1-7 | Create database
R1-8 | Create tables with associated fields
Fill Inventory, Supplier, Distributor, and Customer Tables with Dummy Data
R1-9 | Fill Medical Supplies table with dummy data
R1-10 | Fill Medical Supplier table with dummy data
R1-11 | Fill Distributor table with dummy data
R1-12 | Fill Customer table with dummy data
R1-13 | Write SQL script to designate primary and foreign keys of each table in the database
Create Server and API Interfaces
R1-14 | Develop core functionalities of RESTful server
R1-15 | Create API endpoints for user API interface
R1-16 | Create API endpoints for Medisail API interface
R1-17 | Write SQL script to query data from Inventory Database
R1-18 | Test endpoints in Postman with dummy database data
Database Modification
Fill Inventory, Supplier, Distributor, and Customer Tables with Authentic Data
R1-19 | Fill Medical Supplies table with data in fields: Inventory SKU Number (Integer), Item Name (String), Manufacturer (String), Listing Price (float), Supplier Name (String), Expiration Date (date), Generic Medicine (boolean), Brand Name Medicine (boolean)
R1-20 | Fill Medical Supplier table with data in fields: Supplier ID (Integer), Supplier Name (String), Supplier Primary Address (String), Phone Number (String), Supplier Email (String), Better Business Bureau Rating (String), General Notes (String)
R1-21 | Fill Distributor table with data in fields: Distributor ID (Integer), Distributor Name (String), Distributor Primary Address (String), Phone Number (String), Distributor Email (String), Better Business Bureau Rating (String), General Notes (String)
R1-22 | Fill Customer table with data in fields: Customer ID (Integer), Customer Name (String), Subscription Tier (Integer), Item Purchased (String), Customer Primary Address (String), Phone Number (String), Customer Email (String),
R1-23 | Revise SQL script to query authentic data
R1-24 | Retest API endpoints in Postman to ensure that authentic data is correctly accessed
Implement User Interfaces
R1-25 | Develop marketplace user interface
R1-26 | Develop customer user interface
R1-27 | Develop shopping cart and checkout interface
R1-28 | Develop supplier user interface
R1-29 | Develop Medisail user interface
R1-30 | Develop login interface
Documentation
R1-31 | Write documentation for core system
Test Core System
Unit Testing
R1-32 | Write unit tests for server
R1-33 | Write unit tests for Medisail API interface
R1-34 | Write unit tests for user API interface
R1-35 | Write tests for customer user interface
R1-36 | Write tests for supplier user interface
R1-37 | Write tests for Medisail user interface
R1-38 | Write tests for marketplace interface
R1-39 | Write tests for shopping cart interface
R1-40 | Write tests for checkout interface
R1-41 | Conduct back end unit tests
R1-42 | Conduct user interface tests
R1-43 | Communicate results of unit tests with development team
R1-44 | Modify system based on test results (if needed)
R1-45 | Retest user interfaces
R1-46 | Reteset back end
Integration Testing
R1-47 | Write integration tests between user interfaces and server
R1-48 | Write integration tests between server and database
R1-49 | Write mocked integration tests between user interfaces and database
R1-50 | Conduct integration tests between user interfaces and server
R1-51 | Conduct integration tests between server and database
R1-52 | Conduct integration tests between user interfaces and database
R1-53 | Communicate results of integration tests with development team
R1-54 | Modify system based on test results (if needed)
R1-55 | Retest integration between user interface and server
R1-56 | Retest integration between server and database
R1-57 | Retest integration between user interface and database
System Testing
R1-58 | Write system tests of the entire core system
R1-59 | Conduct system tests of the core system
R1-60 | Communicate results of system tests with development teams
R1-61 | Modify system based on test results (if needed)
R1-62 | Reconduct system tests
Deploy Release 1
Conduct Required Trainings
R1-63 | Train sales manager on core e-procurement system
R1-64 | Train Medisail non-technical employees on core e-procurement system
Pre-Deployment Marketing
R1-65 | Create advertisement materials for core product
R1-66 | Identify pilot customers
Product Deployment
R1-67 | Deploy core system
R1-68 | Monitor system performance after deployment
Collect Customer Feedback
R1-69 | Create customer survey
R1-70 | Send customer survey to pilot customers
R1-71 | Collect and analyze customer feedback
R1-72 | Share customer feedback with team
Release 2: Integrated System
Adjust Plan Based on Customer Feedback
R2-1 | Determine which aspects of feedback are relevant
R2-2 | Revise Release 2 requirements based on feedback assessment
Modify Database Functionality
Make Static Tables Dynamic
R2-3 | Update endpoints in server to allow for database updates
R2-4 | Test mock updates in database
Create Customer Statistics Table
R2-5 | Fill Customer Statistics table with data in fields: Customer ID (Integer), Customer Name (String), Subscription Tier (Integer), Orders per Month (Integer), Average Order Total (float), Monthly Average Order Total (float), Most Purchased Product (String)
Create Supplier Statistics Table
R2-6 | Fill Supplier Statistics table with data in fields: Supplier ID (Integer), Supplier Name (String), Products Purchased per Month (Integer), Most Purchased Product (String), Average Sales per Month (Integer)
R2-7 | Write SQL script to designate primary and foreign keys of new tables in the database
Update Server and API Interfaces
R2-8 | Create endpoints in server to allow for modification of new database tables
R2-9 | Create endpoints in user API interface that allow suppliers to post and remove products from marketplace
R2-10 | Create GET endpoints in Medisail API interface to access customer and supplier statistics data
R2-11 | Develop functionality for statistics charting in Medisail API interface
R2-12 | Test endpoints in Postman
Update User Interfaces
Supplier User Interface
R2-13 | Develop UI components that allow suppliers to post new products to the marketplace
R2-14 | Test user interface to ensure that components correctly map to API endpoints
Medisail User Interface
R2-15 | Develop UI components that allow Medisail employees to view analytics data rendered from API endpoints connected to new database tables
R2-16 | Test user interface to ensure that components correct map to API endpoints
Documentation
R2-17 | Write documentation for integrated system
Test Integrated System
Unit Testing
R2-18 | Write unit tests for new server functionality
R2-19 | Write unit tests for new Medisail API interface endpoints
R2-20 | Write unit tests for user API interface that ensure that customers don't have access to posting new products
R2-21 | Write tests for customer user interface
R2-22 | Write tests for supplier user interface marketplace product posting rendering capabilities
R2-23 | Write tests for Medisail user interface data analytics rendering capabilities
R2-24 | Write tests for marketplace interface to ensure that new product postings are correctly rendered
R2-25 | Write tests for shopping cart interface
R2-26 | Conduct back end unit tests
R2-27 | Conduct user interface tests
R2-28 | Communicate results of unit tests with development team
R2-29 | Modify system based on test results (if needed)
R2-30 | Retest user interfaces
R2-31 | Reteset back end
Integration Testing
R2-32 | Write integration tests between supplier user interface and server
R2-33 | Write integration tests between Medisail user interface and server
R2-34 | Write integration tests between marketplace user interface and server
R2-35 | Write integration tests between user API interface and database
R2-36 | Write integration tests between Medisail API interface and database
R2-37 | Write mocked integration tests between user interfaces and database
R2-38 | Conduct integration tests between user interfaces and server
R2-39 | Conduct integration tests between server and database
R2-40 | Conduct integration tests between user interfaces and database
R2-41 | Communicate results of integration tests with development team
R2-42 | Modify system based on test results (if needed)
R2-43 | Retest integration between user interface and server
R2-44 | Retest integration between server and database
R2-45 | Retest integration between user interface and database
System Testing
R2-46 | Write system tests of the entire integrated system
R2-47 | Conduct system tests of the integrated system
R2-48 | Communicate results of system tests with development teams
R2-49 | Modify system based on test results (if needed)
R2-50 | Reconduct system tests
Deploy Release 2
Conduct Required Trainings
R2-51 | Update sales manager on new capabilities of integrated e-procurement system
R2-52 | Train Medisail non-technical employees on integrated e-procurement system analytics capabilities
Pre-Deployment Marketing
R2-53 | Create advertisement materials for integrated product
Product Deployment
R2-54 | Deploy integrated system
R2-55 | Monitor system performance after deployment
Collect Supplier Feedback on Analytics Capabilities
R2-56 | Create Medisail non-technical employee survey about new analytics capabilities
R2-57 | Create new customer survey with refined prompts based on results of Release 1 survey
R2-58 | Send survey to Medisail non-technical employees who use the system
R2-59 | Send revised survey to customers
R2-60 | Collect and analyze feedback
R2-61 | Share survey feedback with team
Release 3: Advanced System
Adjust Plan Based on Supplier Feedback
R3-1 | Determine which aspects of feedback are relevant
R3-2 | Revise Release 3 requirements based on feedback assessment
Update Backend for Advanced Analytics
User API Interface
R3-3 | Write SQL queries to query analytics data from database for suppliers
R3-4 | Write SQL queries to query analytics data from database for customers
R3-5 | Create endpoints for analytics data for supplier UI
R3-6 | Create endpoints for analytics data for user UI
R3-7 | Test endpoints to ensure that supplier and user analytics data is mapped correctly
Tableau Functionality
R3-8 | Negotiate and obtain Tableau license
R3-9 | Review Tableau documentation
R3-10 | Refine database tables as needed per Tableau documentation
R3-11 | Create Tableau-specific API endpoints for suppliers
R3-12 | Create Tableau-specific API endpoints for customers
R3-13 | Create Tableau-specific API endpoints for Medisail non-technical employees
R3-14 | Test all Tableau endpoints
Update Frontend for Advanced Analytics
R3-15 | Create UI components in customer user interface to render analytics data from database
R3-16 | Create UI components in customer user interface to render Tableau graphics and charts
R3-17 | Create UI components in supplier user interface to render analytics data from database
R3-18 | Create UI components in supplier user interface to render Tableau graphics and charts
R3-19 | Create UI components in Medisail user interface to render Tableau graphics and charts
R3-20 | Test database analytics rendering in customer and supplier user interfaces
R3-21 | Test Tableau integration in all user interfaces
Documentation
R3-22 | Write documentation for advanced system
Test Advanced System
Unit Testing
R3-23 | Write unit tests for data analytics API endpoints to ensure that only applicable data is accessible
R3-24 | Write unit tests for Tableau API endpoints
R3-25 | Write unit tests for new Medisail API interface endpoints to ensure that all data analytics is accessable
R3-26 | Write tests for customer user interface data analytics capabilities
R3-27 | Write tests for supplier user interface data analytics capabilities
R3-28 | Write tests for Medisail user interface data analytics rendering capabilities
R3-29 | Write tests for Tableau integration in customer user interface
R3-30 | Write tests for Tableau integration in supplier user interface
R3-31 | Write tests for Tableau integration in Medisail user interface
R3-32 | Conduct back end unit tests
R3-33 | Conduct user interface tests
R3-34 | Communicate results of unit tests with development team
R3-35 | Modify system based on test results (if needed)
R3-36 | Retest user interfaces
R3-37 | Reteset back end
Integration Testing
R3-38 | Write integration tests between supplier user interface and server
R3-39 | Write integration tests between Medisail user interface and server
R3-40 | Write integration tests between marketplace user interface and server
R3-41 | Write integration tests between user API interface and database
R3-42 | Write integration tests between Medisail API interface and database
R3-43 | Write mocked integration tests between user interfaces and database
R3-44 | Conduct integration tests between user interfaces and server
R3-45 | Conduct integration tests between server and database
R3-46 | Conduct integration tests between user interfaces and database
R3-47 | Communicate results of integration tests with development team
R3-48 | Modify system based on test results (if needed)
R3-49 | Retest integration between user interface and server
R3-50 | Retest integration between server and database
R3-51 | Retest integration between user interface and database
System Testing
R3-52 | Write system tests of the entire advanced system
R3-53 | Conduct system tests of the advanced system
R3-54 | Communicate results of system tests with development teams
R3-55 | Modify system based on test results (if needed)
R3-56 | Reconduct system tests
Deploy Release 3
Conduct Required Trainings
R3-57 | Update sales manager on new capabilities of advanced e-procurement system
R3-58 | Train Medisail non-technical employees on new analytics capabilities
R3-59 | Train customers on new analytics capabilities
R3-60 | Train suppliers on new analytics capabilities
Pre-Deployment Marketing
R3-61 | Create advertisement materials for advanced product
R3-62 | Conduct sales calls with potential new customers
Product Deployment
R3-63 | Deploy advanced system
R3-64 | Monitor system performance after deployment
End of Project Activities
Product Adoption
EOP-1 | Plan product education workshops for customers and suppliers
EOP-2 | Schedule product education workshops
EOP-3 | Conduct product education workshops
EOP-4 | Gather feedback from customers and suppliers during workshops
EOP-5 | Train Medisail sales teams and customer support on product
Continuous Improvement
EOP-6 | Send monthly surveys to customers and suppliers
EOP-7 | Gather feedback from surveys
EOP-8 | Discuss results of surveys
EOP-9 | Determine feasibility of improvements suggested in survey results
EOP-10 | Implement accepted improvements to software system
Note on B3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The low-level wbs doesn't seem to link to the high level
Note on A4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I posted a similar comment to this on the mid level, but I think we should create task numbers that can show tracing to the correct parent from the mid level wbs. for example the high level parent would be PDA-1, the mid level parent to this task would be PDA-1.1, and this task would be PDA-1.1.1 I think this will help show that each task has a parent, and make putting this all into project easier.
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: we might want add a task that will define system usecases in effort to identify all stakeholders and create a draft requirement set.
Note on B6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: After we have a set of requirements do we want to create tasks for additional design steps. high level designs, activity/sequence diagrams, class diagrams, etc.
Note on B14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: in our risk analysis we mention that nosql could help mitigate database related risks. For consistency, we could make this whole section more generic and say things like install and configure the database, and then add another task to trade study data base selection based on system requirements (and any other pre-development design work).

## Effort Estimate WBS
Task Number | Task Name | Resource Type | Resource Name | Team Estimate | PM Estimate | Total Estimate | PM Hours | SRD Hours | BED Hours | FED Hours | DBA Hours | QAT Hours | ITM Hours | SM Hours | SA Hours
Pre-Development Activities
Requirements Analysis
PDA-1 | Gather requirements from stakeholders | FTE (1) | PM | 0 | 2720 | 2720 | 40
PDA-2 | Create software system requirements analysis | FTE (3) | PM, ITM, SRD | 1360 | 680 | 2040 | 10 | 10 |  |  |  |  | 10
PDA-3 | Receive approval of requirements analysis | FTE (1) | PM | 0 | 544 | 544 | 8
| Feasibility Study |  |  | 0 | 0 | 0
PDA-4 | Conduct cash flow analysis | FTE (1) | PM | 0 | 1360 | 1360 | 20
PDA-5 | Conduct risk assessment | FTE (1) | PM | 0 | 1020 | 1020 | 15
Development Environment Setup
PDA-5 | Update laptops to Windows 11 OS | FTE (7) | PM, ITM, SRD, BED, FED, DBA, QAT | 1044 | 136 | 1180 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 8
PDA-6 | Install and configure Visual Studio Code | FTE (6) | ITM, SRD, BED, FED, DBA, QAT | 734 | 0 | 734 |  | 1 | 1 | 1 | 1 | 1 | 1 |  | 8
PDA-7 | Install and configure Postman, Maven, and Junit 5 testing software | FTE (6) | ITM, SRD, BED, FED, DBA, QAT | 1044 | 0 | 1044 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 8
PDA-8 | Install and configure PostgreSQL and SQL interface | FTE (6) | ITM, SRD, BED, FED, DBA, QAT | 1044 | 0 | 1044 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 8
Release 1: Basic (Core) System
Mock Up User Interfaces
R1-1 | Mock up user interface for Medisail customers | FTE (1) | FED | 456 | 0 | 456 |  |  |  | 8
R1-2 | Mock up user interface for suppliers | FTE (1) | FED | 456 | 0 | 456 |  |  |  | 8
R1-3 | Mock up user interface for Medisail non-technical employees | FTE (1) | FED | 456 | 0 | 456 |  |  |  | 8
R1-4 | Mock up marketplace user interface | FTE (1) | FED | 912 | 0 | 912 |  |  |  | 16
R1-5 | Mock up shopping cart and checkout interfaces | FTE (1) | FED | 456 | 0 | 456 |  |  |  | 8
R1-6 | Mock up login portal user interface | FTE (1) | FED | 228 | 0 | 228 |  |  |  | 4
Database Creation
R1-7 | Create database | FTE (1) | DBA | 136 | 0 | 136 |  |  |  |  | 4
R1-8 | Create tables with associated fields | FTE (1) | DBA | 136 | 0 | 136 |  |  |  |  | 4
Fill Inventory, Supplier, Distributor, and Customer Tables with Dummy Data
R1-9 | Fill Medical Supplies table with dummy data | FTE (1) | DBA | 272 | 0 | 272 |  |  |  |  | 8
R1-10 | Fill Medical Supplier table with dummy data | FTE (1) | DBA | 272 | 0 | 272 |  |  |  |  | 8
R1-11 | Fill Distributor table with dummy data | FTE (1) | DBA | 272 | 0 | 272 |  |  |  |  | 8
R1-12 | Fill Customer table with dummy data | FTE (1) | DBA | 272 | 0 | 272 |  |  |  |  | 8
R1-13 | Write SQL script to designate primary and foreign keys of each table in the database | FTE(1) | DBA | 272 | 0 | 272 |  |  |  |  | 8
Create Server and API Interfaces
R1-14 | Develop core functionalities of RESTful server | FTE (1) | BED | 1392 | 0 | 1392 |  |  | 24
R1-15 | Create API endpoints for user API interface | FTE (1) | BED | 464 | 0 | 464 |  |  | 8
R1-16 | Create API endpoints for Medisail API interface | FTE (1) | BED | 464 | 0 | 464 |  |  | 8
R1-17 | Write SQL script to query data from Inventory Database | FTE (1) | BED | 928 | 0 | 928 |  |  | 16
R1-18 | Test endpoints in Postman | FTE (1) | BED | 232 | 0 | 232 |  |  | 4
Database Modification
Fill Inventory, Supplier, Distributor, and Customer Tables with Authentic Data
R1-19 | Fill Medical Supplies table with data in fields: Inventory SKU Number (Integer), Item Name (String), Manufacturer (String), Listing Price (float), Supplier Name (String), Expiration Date (date), Generic Medicine (boolean), Brand Name Medicine (boolean) | FTE (1) | DBA | 408 | 0 | 408 |  |  |  |  | 12
R1-20 | Fill Medical Supplier table with data in fields: Supplier ID (Integer), Supplier Name (String), Supplier Primary Address (String), Phone Number (String), Supplier Email (String), Better Business Bureau Rating (String), General Notes (String) | FTE (1) | DBA | 408 | 0 | 408 |  |  |  |  | 12
R1-21 | Fill Distributor table with data in fields: Distributor ID (Integer), Distributor Name (String), Distributor Primary Address (String), Phone Number (String), Distributor Email (String), Better Business Bureau Rating (String), General Notes (String) | FTE (1) | DBA | 408 | 0 | 408 |  |  |  |  | 12
R1-22 | Fill Customer table with data in fields: Customer ID (Integer), Customer Name (String), Subscription Tier (Integer), Item Purchased (String), Customer Primary Address (String), Phone Number (String), Customer Email (String), | FTE (1) | DBA | 408 | 0 | 408 |  |  |  |  | 12
R1-23 | Revise SQL script to query authentic data | FTE (1) | DBA | 408 | 0 | 408 |  |  |  |  | 12
R1-24 | Retest API endpoints in Postman to ensure that authentic data is correctly accessed | FTE (1) | BED | 136 | 0 | 136 |  |  |  |  | 4
Implement User Interfaces
R1-25 | Develop marketplace user interface | FTE (1) | FED | 1368 | 0 | 1368 |  |  |  | 24
R1-26 | Develop customer user interface | FTE (1) | FED | 912 | 0 | 912 |  |  |  | 16
R1-27 | Develop shopping cart and checkout interface | FTE (1) | FED | 912 | 0 | 912 |  |  |  | 16
R1-28 | Develop supplier user interface | FTE (1) | FED | 912 | 0 | 912 |  |  |  | 16
R1-29 | Develop Medisail user interface | FTE (1) | FED | 912 | 0 | 912 |  |  |  | 16
R1-30 | Develop login interface | FTE (1) | FED | 456 | 0 | 456 |  |  |  | 8
Documentation
R1-31 | Write documentation for core system | FTE (2) | SRD, ITM | 2720 | 0 | 2720 |  | 20 |  |  |  |  | 20
Test Core System
Unit Testing
R1-32 | Write unit tests for server | FTE (1) | QAT | 200 | 0 | 200 | [5 empty] | 8
R1-33 | Write unit tests for Medisail API interface | FTE (1) | QAT | 200 | 0 | 200 | [5 empty] | 8
R1-34 | Write unit tests for user API interface | FTE (1) | QAT | 200 | 0 | 200 | [5 empty] | 8
R1-35 | Write tests for customer user interface | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R1-36 | Write tests for supplier user interface | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R1-37 | Write tests for Medisail user interface | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R1-38 | Write tests for marketplace interface | FTE (1) | QAT | 600 | 0 | 600 | [5 empty] | 24
R1-39 | Write tests for shopping cart interface | FTE (1) | QAT | 250 | 0 | 250 | [5 empty] | 10
R1-40 | Write tests for checkout interface | FTE (1) | QAT | 300 | 0 | 300 | [5 empty] | 12
R1-41 | Conduct back end unit tests | FTE (1) | QAT | 300 | 0 | 300 | [5 empty] | 12
R1-42 | Conduct user interface tests | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R1-43 | Communicate results of unit tests with development team | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R1-44 | Modify system based on test results (if needed) | FTE (1) | QAT | 350 | 0 | 350 | [5 empty] | 14
R1-45 | Retest user interfaces | FTE (3) | QAT, ITM, SRD | 744 | 544 | 1288 | 8 |  |  |  |  | 8 | 8
R1-46 | Reteset back end | FTE (3) | SRD, BED, FED | 7320 | 0 | 7320 |  | 40 | 40 | 40
R1-47 | Retest user interfaces | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R1-48 | Reteset back end | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
Integration Testing
R1-49 | Write integration tests between user interfaces and server | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R1-44 | Write integration tests between server and database | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R1-45 | Write mocked integration tests between user interfaces and database | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R1-46 | Conduct integration tests between user interfaces and server | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R1-47 | Conduct integration tests between server and database | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R1-48 | Conduct integration tests between user interfaces and database | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R1-49 | Communicate results of integration tests with development team | FTE (3) | QAT, ITM, SRD | 744 | 544 | 1288 | 8 |  |  |  |  | 8 | 8
R1-50 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 14640 | 0 | 14640 |  | 80 | 80 | 80
R1-51 | Retest integration between user interface and server | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R1-52 | Retest integration between server and database | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R1-53 | Retest integration between user interface and database | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
System Testing
R1-54 | Write system tests of the entire core system | FTE (1) | QAT | 600 | 0 | 600 | [5 empty] | 24
R1-55 | Conduct system tests of the core system | FTE (3) | QAT, SRD, PM | 3720 | 2720 | 6440 | 40 | 40 |  |  |  | 40
R1-56 | Communicate results of system tests with development teams | FTE (3) | QAT, SRD, PM | 1088 | 544 | 1632 | 8 | 8 |  |  |  |  | 8
R1-57 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 14640 | 0 | 14640 |  | 80 | 80 | 80
R1-58 | Reconduct system tests | FTE (3) | QAT, SRD, PM | 1488 | 1088 | 2576 | 16 | 16 |  |  |  | 16
R1-59 | Deploy Release 1
Conduct Required Trainings
R1-60 | Train sales manager on core e-procurement system | FTE (2) | PM, SM | 2520 | 2720 | 5240 | 40 | [6 empty] | 40
R1-61 | Train Medisail non-technical employees on core e-procurement system | FTE (1) | PM | 0 | 1088 | 1088 | 16
Pre-Deployment Marketing
R1-61 | Create advertisement materials for core product | FTE (1) | SM | 1008 | 0 | 1008 | [7 empty] | 16
R1-62 | Identify pilot customers | FTE (1) | SM | 1512 | 0 | 1512 | [7 empty] | 24
Product Deployment
R1-63 | Deploy core system | FTE (1) | SRD | 272 | 0 | 272 |  | 4
R1-64 | Monitor system performance after deployment | FTE (1) | SRD | 2720 | 0 | 2720 |  | 40
Collect Customer Feedback
R1-65 | Create customer survey | FTE (1) | SM | 252 | 0 | 252 | [7 empty] | 4
R1-66 | Send customer survey to pilot customers | FTE (1) | SM | 63 | 0 | 63 | [7 empty] | 1
R1-67 | Collect and analyze customer feedback | FTE (1) | SM | 1008 | 0 | 1008 | [7 empty] | 16
R1-68 | Share customer feedback with team | FTE (1) | SM | 252 | 0 | 252 | [7 empty] | 4
Release 2: Integrated System
Adjust Plan Based on Customer Feedback
R2-1 | Determine which aspects of feedback are relevant | FTE (2) | PM, SRD | 544 | 544 | 1088 | 8 | 8
R2-2 | Revise Release 2 requirements based on feedback assessment | FTE (2) | PM, SRD | 544 | 544 | 1088 | 8 | 8
Modify Database Functionality
Make Static Tables Dynamic
R2-3 | Update endpoints in server to allow for database updates | FTE (1) | BED | 928 | 0 | 928 |  |  | 16
R2-4 | Test mock updates in database | FTE (1) | BED | 464 | 0 | 464 |  |  | 8
Create Customer Statistics Table
R2-5 | Fill Customer Statistics table with data in fields: Customer ID (Integer), Customer Name (String), Subscription Tier (Integer), Orders per Month (Integer), Average Order Total (float), Monthly Average Order Total (float), Most Purchased Product (String) | FTE (1) | DBA | 272 | 0 | 272 |  |  |  |  | 8
Create Supplier Statistics Table
R2-6 | Fill Supplier Statistics table with data in fields: Supplier ID (Integer), Supplier Name (String), Products Purchased per Month (Integer), Most Purchased Product (String), Average Sales per Month (Integer) | FTE (1) | DBA | 272 | 0 | 272 |  |  |  |  | 8
R2-7 | Write SQL script to designate primary and foreign keys of new tables in the database | FTE (1) | DBA | 464 | 0 | 464 |  |  | 8
| Update Server and API Interfaces |  |  | 0 | 0 | 0
R2-8 | Create endpoints in server to allow for modification of new database tables | FTE (1) | BED | 464 | 0 | 464 |  |  | 8
R2-9 | Create endpoints in user API interface that allow suppliers to post and remove products from marketplace | FTE (1) | BED | 464 | 0 | 464 |  |  | 8
R2-10 | Create GET endpoints in Medisail API interface to access customer and supplier statistics data | FTE (1) | BED | 464 | 0 | 464 |  |  | 8
R2-11 | Develop functionality for statistics charting in Medisail API interface | FTE (1) | BED | 2320 | 0 | 2320 |  |  | 40
R2-12 | Test endpoints in Postman | FTE (1) | BED | 928 | 0 | 928 |  |  | 16
Update User Interfaces
Supplier User Interface
R2-13 | Develop UI components that allow suppliers to post new products to the marketplace | FTE (1) | FED | 1368 | 0 | 1368 |  |  |  | 24
R2-14 | Test user interface to ensure that components correctly map to API endpoints | FTE (1) | FED | 456 | 0 | 456 |  |  |  | 8
Medisail User Interface
R2-15 | Develop UI components that allow Medisail employees to view analytics data rendered from API endpoints connected to new database tables | FTE (1) | FED | 1824 | 0 | 1824 |  |  |  | 32
R2-16 | Test user interface to ensure that components correct map to API endpoints | FTE (1) | FED | 912 | 0 | 912 |  |  |  | 16
Documentation
R2-17 | Write documentation for integrated system | FTE (2) | SRD, ITM | 2720 | 0 | 2720 |  | 20 |  |  |  |  | 20
Test Integrated System
Unit Testing
R2-18 | Write unit tests for new server functionality | FTE (1) | QAT | 200 | 0 | 200 | [5 empty] | 8
R2-19 | Write unit tests for new Medisail API interface endpoints | FTE (1) | QAT | 200 | 0 | 200 | [5 empty] | 8
R2-20 | Write unit tests for user API interface that ensure that customers don't have access to posting new products | FTE (1) | QAT | 200 | 0 | 200 | [5 empty] | 8
R2-21 | Write tests for customer user interface | FTE (1) | QAT | 100 | 0 | 100 | [5 empty] | 4
R2-22 | Write tests for supplier user interface marketplace product posting rendering capabilities | FTE (1) | QAT | 200 | 0 | 200 | [5 empty] | 8
R2-23 | Write tests for Medisail user interface data analytics rendering capabilities | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R2-24 | Write tests for marketplace interface to ensure that new product postings are correctly rendered | FTE (1) | QAT | 200 | 0 | 200 | [5 empty] | 8
R2-25 | Write tests for shopping cart interface | FTE (1) | QAT | 100 | 0 | 100 | [5 empty] | 4
R2-26 | Conduct back end unit tests | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R2-27 | Conduct user interface tests | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R2-28 | Communicate results of unit tests with development team | FTE (3) | QAT, ITM, SRD | 2576 | 0 | 2576 |  | 16 |  |  |  | 16 | 16
R2-29 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 7320 | 0 | 7320 |  | 40 | 40 | 40
R2-30 | Retest user interfaces | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R2-31 | Reteset back end | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
Integration Testing
R2-32 | Write integration tests between supplier user interface and server | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R2-33 | Write integration tests between Medisail user interface and server | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R2-34 | Write integration tests between marketplace user interface and server | FTE (1) | QAT | 200 | 0 | 200 | [5 empty] | 8
R2-35 | Write integration tests between user API interface and database | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R2-36 | Write integration tests between Medisail API interface and database | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R2-37 | Write mocked integration tests between user interfaces and database | FTE (1) | QAT | 100 | 0 | 100 | [5 empty] | 4
R2-38 | Conduct integration tests between user interfaces and server | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R2-39 | Conduct integration tests between server and database | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R2-40 | Conduct integration tests between user interfaces and database | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R2-41 | Communicate results of integration tests with development team | FTE (3) | QAT, ITM, SRD | 1288 | 0 | 1288 |  | 8 |  |  |  | 8 | 8
R2-42 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 9840 | 0 | 9840 |  | 60 | 60 | 40
R2-43 | Retest integration between user interface and server | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R2-44 | Retest integration between server and database | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R2-45 | Retest integration between user interface and database | FTE (1) | QAT | 200 | 0 | 200 | [5 empty] | 8
System Testing
R2-46 | Write system tests of the entire integrated system | FTE (1) | QAT | 600 | 0 | 600 | [5 empty] | 24
R2-47 | Conduct system tests of the integrated system | FTE (3) | QAT, SRD, PM | 600 | 0 | 600 | [5 empty] | 24
R2-48 | Communicate results of system tests with development teams | FTE (3) | QAT, SRD, PM | 744 | 544 | 1288 | 8 | 8 |  |  |  | 8
R2-49 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 9840 | 0 | 9840 |  | 60 | 60 | 40
R2-50 | Reconduct system tests | FTE (3) | QAT, SRD, PM | 1688 | 1088 | 2776 | 16 | 16 |  |  |  | 24
Deploy Release 2
Conduct Required Trainings
R2-51 | Update sales manager on new capabilities of integrated e-procurement system | FTE (2) | PM, SM | 1008 | 1088 | 2096 | 16 | [6 empty] | 16
R2-52 | Train Medisail non-technical employees on integrated e-procurement system analytics capabilities | FTE (1) | PM | 0 | 1632 | 1632 | 24
Pre-Deployment Marketing
R2-53 | Create advertisement materials for integrated product | FTE (1) | SM | 504 | 0 | 504 | [7 empty] | 8
| Product Deployment |  |  | 0 | 0 | 0
R2-54 | Deploy integrated system | FTE (1) | SRD | 544 | 0 | 544 |  | 8
R2-55 | Monitor system performance after deployment | FTE (1) | SRD | 2720 | 0 | 2720 |  | 40
Collect Supplier Feedback on Analytics Capabilities
R2-56 | Create Medisail non-technical employee survey about new analytics capabilities | FTE (1) | SM | 126 | 0 | 126 | [7 empty] | 2
R2-57 | Create new customer survey with refined prompts based on results of Release 1 survey | FTE (1) | SM | 126 | 0 | 126 | [7 empty] | 2
R2-58 | Send survey to Medisail non-technical employees who use the system | FTE (1) | SM | 252 | 0 | 252 | [7 empty] | 4
R2-59 | Send revised survey to customers | FTE (1) | SM | 63 | 0 | 63 | [7 empty] | 1
R2-60 | Collect and analyze feedback | FTE (1) | SM | 1008 | 0 | 1008 | [7 empty] | 16
R2-61 | Share survey feedback with team | FTE (1) | SM | 252 | 0 | 252 | [7 empty] | 4
Release 3: Advanced System
Adjust Plan Based on Supplier Feedback
R3-1 | Determine which aspects of feedback are relevant | FTE (2) | PM, SRD | 544 | 544 | 1088 | 8 | 8
R3-2 | Revise Release 3 requirements based on feedback assessment | FTE (2) | PM, SRD | 544 | 544 | 1088 | 8 | 8
Update Backend for Advanced Analytics
User API Interface
R3-3 | Write SQL queries to query analytics data from database for suppliers | FTE (1) | DBA | 544 | 0 | 544 |  |  |  |  | 16
R3-4 | Write SQL queries to query analytics data from database for customers | FTE (1) | DBA | 544 | 0 | 544 |  |  |  |  | 16
R3-5 | Create endpoints for analytics data for supplier UI | FTE (1) | BED | 464 | 0 | 464 |  |  | 8
R3-6 | Create endpoints for analytics data for user UI | FTE (1) | BED | 464 | 0 | 464 |  |  | 8
R3-7 | Test endpoints to ensure that supplier and user analytics data is mapped correctly | FTE (1) | BED | 1160 | 0 | 1160 |  |  | 20
Tableau Functionality
R3-8 | Negotiate and obtain Tableau licence | FTE (1) | PM | 0 | 2720 | 2720 | 40
R3-9 | Review Tableau documentation | FTE (2) | DBA, BED | 2208 | 0 | 2208 |  |  | 24 |  | 24
R3-10 | Refine database tables as needed per Tableau documentation | FTE (1) | DBA | 1088 | 0 | 1088 |  |  |  |  | 32
R3-11 | Create Tableau-specific API endpoints for suppliers | FTE (1) | BED | 928 | 0 | 928 |  |  | 16
R3-12 | Create Tableau-specific API endpoints for customers | FTE (1) | BED | 928 | 0 | 928 |  |  | 16
R3-13 | Create Tableau-specific API endpoints for Medisail non-technical employees | FTE (1) | BED | 928 | 0 | 928 |  |  | 16
R3-14 | Test all Tableau endpoints | FTE (2) | DBA, BED | 2208 | 0 | 2208 |  |  | 24 |  | 24
Update Frontend for Advanced Analytics
R3-15 | Create UI components in customer user interface to render analytics data from database | FTE (1) | FED | 2280 | 0 | 2280 |  |  |  | 40
R3-16 | Create UI components in customer user interface to render Tableau graphics and charts | FTE (2) | FED, SRD | 3000 | 0 | 3000 |  | 24 |  | 24
R3-17 | Create UI components in supplier user interface to render analytics data from database | FTE (1) | FED | 2280 | 0 | 2280 |  |  |  | 40
R3-18 | Create UI components in supplier user interface to render Tableau graphics and charts | FTE (2) | FED, SRD | 3000 | 0 | 3000 |  | 24 |  | 24
R3-19 | Create UI components in Medisail user interface to render Tableau graphics and charts | FTE (2) | FED, SRD | 3000 | 0 | 3000 |  | 24 |  | 24
R3-20 | Test database analytics rendering in customer and supplier user interfaces | FTE (2) | FED, SRD | 2000 | 0 | 2000 |  | 16 |  | 16
R3-21 | Test Tableau integration in all user interfaces | FTE (2) | FED, SRD | 2500 | 0 | 2500 |  | 20 |  | 20
Documentation
R3-22 | Write documentation for advanced system | FTE (2) | SRD, ITM | 5440 | 0 | 5440 |  | 40 |  |  |  |  | 40
Test Advanced System
Unit Testing
R3-23 | Write unit tests for data analytics API endpoints to ensure that only applicable data is accessible | FTE (1) | QAT | 300 | 0 | 300 | [5 empty] | 12
R3-24 | Write unit tests for Tableau API endpoints | FTE (1) | QAT | 300 | 0 | 300 | [5 empty] | 12
R3-25 | Write unit tests for new Medisail API interface endpoints to ensure that all data analytics is accessable | FTE (1) | QAT | 300 | 0 | 300 | [5 empty] | 12
R3-26 | Write tests for customer user interface data analytics capabilities | FTE (1) | QAT | 200 | 0 | 200 | [5 empty] | 8
R3-27 | Write tests for supplier user interface data analytics capabilities | FTE (1) | QAT | 200 | 0 | 200 | [5 empty] | 8
R3-28 | Write tests for Medisail user interface data analytics rendering capabilities | FTE (1) | QAT | 300 | 0 | 300 | [5 empty] | 12
R3-29 | Write tests for Tableau integration in customer user interface | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R3-30 | Write tests for Tableau integration in supplier user interface | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R3-31 | Write tests for Tableau integration in Medisail user interface | FTE (1) | QAT | 500 | 0 | 500 | [5 empty] | 20
R3-32 | Conduct back end unit tests | FTE (1) | QAT | 1000 | 0 | 1000 | [5 empty] | 40
R3-33 | Conduct user interface tests | FTE (1) | QAT | 800 | 0 | 800 | [5 empty] | 32
R3-34 | Communicate results of unit tests with development team | FTE (3) | QAT, ITM, SRD | 1464 | 0 | 1464 |  | 8 | 8 | 8
R3-35 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 7320 | 0 | 7320 |  | 40 | 40 | 40
R3-36 | Retest user interfaces | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R3-37 | Reteset back end | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
Integration Testing
R3-38 | Write integration tests between supplier user interface and server | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R3-39 | Write integration tests between Medisail user interface and server | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R3-40 | Write integration tests between marketplace user interface and server | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R3-41 | Write integration tests between user API interface and database | FTE (1) | QAT | 500 | 0 | 500 | [5 empty] | 20
R3-42 | Write integration tests between Medisail API interface and database | FTE (1) | QAT | 500 | 0 | 500 | [5 empty] | 20
R3-43 | Write mocked integration tests between user interfaces and database | FTE (1) | QAT | 300 | 0 | 300 | [5 empty] | 12
R3-44 | Conduct integration tests between user interfaces and server | FTE (1) | QAT | 200 | 0 | 200 | [5 empty] | 8
R3-45 | Conduct integration tests between server and database | FTE (1) | QAT | 200 | 0 | 200 | [5 empty] | 8
R3-46 | Conduct integration tests between user interfaces and database | FTE (1) | QAT | 200 | 0 | 200 | [5 empty] | 8
R3-47 | Communicate results of integration tests with development team | FTE (3) | QAT, ITM, SRD | 1288 | 0 | 1288 |  | 8 |  |  |  | 8 | 8
R3-48 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 10980 | 0 | 10980 |  | 60 | 60 | 60
R3-49 | Retest integration between user interface and server | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R3-50 | Retest integration between server and database | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
R3-51 | Retest integration between user interface and database | FTE (1) | QAT | 400 | 0 | 400 | [5 empty] | 16
System Testing
R3-52 | Write system tests of the entire advanced system | FTE (1) | QAT | 600 | 0 | 600 | [5 empty] | 24
R3-53 | Conduct system tests of the advanced system | FTE (3) | QAT, SRD, PM | 400 | 0 | 400 | [5 empty] | 16
R3-54 | Communicate results of system tests with development teams | FTE (3) | QAT, SRD, PM | 1632 | 1088 | 2720 | 16 | 16 |  |  | 16
R3-55 | Modify system based on test results (if needed) | FTE (3) | SRD, BED, FED | 14640 | 0 | 14640 |  | 80 | 80 | 80
R3-56 | Reconduct system tests | FTE (3) | QAT, SRD, PM | 800 | 0 | 800 | [5 empty] | 32
Deploy Release 3
Conduct Required Trainings
R3-57 | Update sales manager on new capabilities of advanced e-procurement system | FTE (2) | PM, SM | 1512 | 1632 | 3144 | 24 | [6 empty] | 24
R3-58 | Train Medisail non-technical employees on new analytics capabilities | FTE (1) | PM | 1008 | 0 | 1008 | [7 empty] | 16
R3-59 | Train customers on new analytics capabilities | FTE (1) | PM | 756 | 0 | 756 | [7 empty] | 12
R3-60 | Train suppliers on new analytics capabilities | FTE (1) | PM | 756 | 0 | 756 | [7 empty] | 12
| Pre-Deployment Marketing |  |  | 0 | 0 | 0
R3-61 | Create advertisement materials for advanced product | FTE (1) | SM | 504 | 0 | 504 | [7 empty] | 8
R3-62 | Conduct sales calls with potential new customers | FTE (1) | SM | 504 | 0 | 504 | [7 empty] | 8
R3-63 | Product Deployment |  |  | 5040 | 0 | 5040 | [7 empty] | 80
| Deploy advanced system | FTE (1) | SRD | 544 | 0 | 544 |  | 8
R3-64 | Monitor system performance after deployment | FTE (1) | SRD | 2720 | 0 | 2720 |  | 40
End of Project Activities
Product Adoption
EOP-1 | Plan product education workshops for customers and suppliers | FTE (2) | PM, SM | 756 | 816 | 1572 | 12 | [6 empty] | 12
EOP-2 | Schedule product education workshops | FTE (1) | SM | 126 | 0 | 126 | [7 empty] | 2
EOP-3 | Conduct product education workshops | FTE (1) | SM | 2520 | 0 | 2520 | [7 empty] | 40
EOP-4 | Gather feedback from customers and suppliers during workshops | FTE (1) | SM | 504 | 0 | 504 | [7 empty] | 8
EOP-5 | Train Medisail sales teams and customer support on product | FTE (2) | PM, SM | 1008 | 1088 | 2096 | 16 | [6 empty] | 16
Continuous Improvement
EOP-6 | Send monthly surveys to customers and suppliers | FTE (1) | SM | 126 | 0 | 126 | [7 empty] | 2
EOP-7 | Gather feedback from surveys | FTE (1) | SM | 504 | 0 | 504 | [7 empty] | 8
EOP-8 | Discuss results of surveys | FTE (2) | PM, SM | 504 | 544 | 1048 | 8 | [6 empty] | 8
EOP-9 | Determine feasibility of improvements suggested in survey results | FTE (3) | PM, SRD, ITM | 2176 | 1088 | 3264 | 16 | 16 |  |  |  |  | 16
EOP-10 | Implement accepted improvements to software system | FTE (3) | SRD, BED, FED | 7320 | 0 | 7320 |  | 40 | 40 | 40
|  | Total Effort Estimate: |  | 264732 | 31212 | 295944 | 459 | 1117 | 899 | 971 | 263 | 1323 | 169 | 414 | 32

## Risk Estimate WBS
Task Number | Task Name | Optimistic | Most Likely | Pessimistic | Risk | Estimate
Pre-Development Activities
Requirements Analysis
PDA-1 | Gather requirements from stakeholders | 5 | 7 | 9 | Low | 5
PDA-2 | Create software system requirements analysis | 5 | 7 | 9 | Low | 5
PDA-3 | Receive approval of requirements analysis | 1 | 2 | 3 | Low | 1
Feasibility Study
PDA-4 | Conduct cash flow analysis | 4 | 6 | 8 | Medium | 6
PDA-5 | Conduct risk assessment | 5 | 7 | 9 | High | 9
Development Environment Setup
PDA-5 | Update laptops to Windows 11 OS | 1 | 1 | 2 | Low | 1
PDA-6 | Install and configure Visual Studio Code | 1 | 1 | 2 | Low | 1
PDA-7 | Install and configure Postman, Maven, and Junit 5 testing software | 5 | 6 | 7 | Low | 5
PDA-8 | Install and configure PostgreSQL and SQL interface | 5 | 6 | 6 | Low | 5
Release 1: Basic (Core) System
Mock Up User Interfaces
R1-1 | Mock up user interface for Medisail customers | 2 | 5 | 3 | Medium | 5
R1-2 | Mock up user interface for suppliers | 1 | 5 | 3 | Medium | 5
R1-3 | Mock up user interface for Medisail non-technical employees | 2 | 4 | 2 | Low | 2
R1-4 | Mock up marketplace user interface | 2 | 3 | 5 | Medium | 3
R1-5 | Mock up shopping cart and checkout interfaces | 2 | 5 | 6 | High | 6
R1-6 | Mock up login portal user interface | 5 | 6 | 7 | Medium | 6
Database Creation
R1-7 | Create database | 2 | 4 | 6 | Low | 2
R1-8 | Create tables with associated fields | 4 | 6 | 9 | Low | 4
Fill Inventory, Supplier, Distributor, and Customer Tables with Dummy Data
R1-9 | Fill Medical Supplies table with dummy data | 2 | 7 | 1 | Low | 2
R1-10 | Fill Medical Supplier table with dummy data | 2 | 7 | 1 | Low | 2
R1-11 | Fill Distributor table with dummy data | 2 | 7 | 1 | Low | 2
R1-12 | Fill Customer table with dummy data | 2 | 7 | 1 | Low | 2
R1-13 | Write SQL script to designate primary and foreign keys of each table in the database | 2 | 2 | 3 | Medium | 2
Create Server and API Interfaces
R1-14 | Develop core functionalities of RESTful server | 4 | 5 | 8 | High | 8
R1-15 | Create API endpoints for user API interface | 3 | 4 | 7 | Medium | 4
R1-16 | Create API endpoints for Medisail API interface | 3 | 4 | 7 | Medium | 4
R1-17 | Write SQL script to query data from Inventory Database | 3 | 4 | 7 | Low | 3
R1-18 | Test endpoints in Postman with dummy database data | 1 | 2 | 3 | Medium | 2
Database Modification
Fill Inventory, Supplier, Distributor, and Customer Tables with Authentic Data
R1-19 | Fill Medical Supplies table with data in fields: Inventory SKU Number (Integer), Item Name (String), Manufacturer (String), Listing Price (float), Supplier Name (String), Expiration Date (date), Generic Medicine (boolean), Brand Name Medicine (boolean) | 1 | 3 | 6 | Medium | 3
R1-20 | Fill Medical Supplier table with data in fields: Supplier ID (Integer), Supplier Name (String), Supplier Primary Address (String), Phone Number (String), Supplier Email (String), Better Business Bureau Rating (String), General Notes (String) | 1 | 3 | 6 | Medium | 3
R1-21 | Fill Distributor table with data in fields: Distributor ID (Integer), Distributor Name (String), Distributor Primary Address (String), Phone Number (String), Distributor Email (String), Better Business Bureau Rating (String), General Notes (String) | 1 | 3 | 6 | Medium | 3
R1-22 | Fill Customer table with data in fields: Customer ID (Integer), Customer Name (String), Subscription Tier (Integer), Item Purchased (String), Customer Primary Address (String), Phone Number (String), Customer Email (String), | 1 | 3 | 6 | Medium | 3
R1-23 | Revise SQL script to query authentic data | 1 | 3 | 6 | High | 6
R1-24 | Retest API endpoints in Postman to ensure that authentic data is correctly accessed | 1 | 2 | 2 | Low | 1
Implement User Interfaces
R1-25 | Develop marketplace user interface | 1 | 1 | 4 | Low | 1
R1-26 | Develop customer user interface | 1 | 1 | 4 | Low | 1
R1-27 | Develop shopping cart and checkout interface | 1 | 1 | 4 | Low | 1
R1-28 | Develop supplier user interface | 2 | 3 | 4 | Medium | 3
R1-29 | Develop Medisail user interface | 2 | 3 | 3 | Medium | 3
R1-30 | Develop login interface | 1 | 2 | 3 | Medium | 2
Documentation
R1-31 | Write documentation for core system | 1 | 2 | 3 | Medium | 2
Test Core System
Unit Testing
R1-32 | Write unit tests for server | 3 | 4 | 4 | Medium | 4
R1-33 | Write unit tests for Medisail API interface | 2 | 3 | 4 | Medium | 3
R1-34 | Write unit tests for user API interface | 2 | 3 | 4 | Medium | 3
R1-35 | Write tests for customer user interface | 1 | 1 | 2 | Low | 1
R1-36 | Write tests for supplier user interface | 1 | 2 | 3 | Medium | 2
R1-37 | Write tests for Medisail user interface | 1 | 1 | 2 | Low | 1
R1-38 | Write tests for marketplace interface | 1 | 2 | 3 | Medium | 2
R1-39 | Write tests for shopping cart interface | 1 | 2 | 3 | Medium | 2
R1-40 | Write tests for checkout interface | 2 | 3 | 4 | Medium | 3
R1-41 | Conduct back end unit tests | 2 | 3 | 4 | Medium | 3
R1-42 | Conduct user interface tests | 1 | 2 | 3 | Medium | 2
R1-43 | Communicate results of unit tests with development team | 2 | 3 | 4 | Medium | 3
R1-44 | Modify system based on test results (if needed) | 2 | 3 | 4 | Medium | 3
R1-45 | Retest user interfaces | 2 | 3 | 4 | Medium | 3
R1-46 | Reteset back end | 1 | 1 | 2 | Low | 1
Integration Testing
R1-47 | Write integration tests between user interfaces and server | 1 | 2 | 3 | Medium | 2
R1-48 | Write integration tests between server and database | 1 | 2 | 3 | Medium | 2
R1-49 | Write mocked integration tests between user interfaces and database | 1 | 2 | 3 | Medium | 2
R1-50 | Conduct integration tests between user interfaces and server | 2 | 4 | 5 | High | 5
R1-51 | Conduct integration tests between server and database | 2 | 4 | 5 | High | 5
R1-52 | Conduct integration tests between user interfaces and database | 3 | 5 | 7 | High | 7
R1-53 | Communicate results of integration tests with development team | 1 | 1 | 2 | Low | 1
R1-54 | Modify system based on test results (if needed) | 1 | 2 | 3 | Medium | 2
R1-55 | Retest integration between user interface and server | 1 | 2 | 3 | Medium | 2
R1-56 | Retest integration between server and database | 1 | 2 | 3 | Medium | 2
R1-57 | Retest integration between user interface and database | 1 | 2 | 3 | Medium | 2
System Testing
R1-58 | Write system tests of the entire core system | 1 | 2 | 3 | Medium | 2
R1-59 | Conduct system tests of the core system | 2 | 4 | 5 | High | 5
R1-60 | Communicate results of system tests with development teams | 2 | 4 | 5 | High | 5
R1-61 | Modify system based on test results (if needed) | 3 | 5 | 7 | High | 7
R1-62 | Reconduct system tests | 2 | 3 | 4 | Medium | 3
Deploy Release 1
Conduct Required Trainings
R1-63 | Train sales manager on core e-procurement system | 3 | 4 | 5 | Medium | 4
R1-64 | Train Medisail non-technical employees on core e-procurement system | 2 | 3 | 4 | Medium | 3
R1-65 | Create advertisement materials for core product | 2 | 3 | 4 | Medium | 3
R1-66 | Identify pilot customers | 1 | 1 | 2 | Low | 1
Product Deployment
R1-67 | Deploy core system | 1 | 2 | 3 | Medium | 2
R1-68 | Monitor system performance after deployment | 4 | 5 | 6 | Medium | 5
Collect Customer Feedback
R1-69 | Create customer survey | 1 | 1 | 2 | Low | 1
R1-70 | Send customer survey to pilot customers | 2 | 2 | 3 | Low | 2
R1-71 | Collect and analyze customer feedback | 1 | 2 | 3 | Medium | 2
R1-72 | Share customer feedback with team | 1 | 2 | 3 | Medium | 2
Release 2: Integrated System
Adjust Plan Based on Customer Feedback
R2-1 | Determine which aspects of feedback are relevant | 1 | 1 | 2 | Low | 1
R2-2 | Revise Release 2 requirements based on feedback assessment | 3 | 4 | 3 | Medium | 4
| Modify Database Functionality | 3 | 4 | 3 | Medium | 4
Make Static Tables Dynamic
R2-3 | Update endpoints in server to allow for database updates | 1 | 3 | 4 | Medium | 3
R2-4 | Test mock updates in database | 2 | 3 | 4 | Medium | 3
Create Customer Statistics Table
R2-5 | Fill Customer Statistics table with data in fields: Customer ID (Integer), Customer Name (String), Subscription Tier (Integer), Orders per Month (Integer), Average Order Total (float), Monthly Average Order Total (float), Most Purchased Product (String) | 2 | 4 | 5 | Medium | 4
| Create Supplier Statistics Table | 3 | 4 | 5 | Medium | 4
R2-6 | Fill Supplier Statistics table with data in fields: Supplier ID (Integer), Supplier Name (String), Products Purchased per Month (Integer), Most Purchased Product (String), Average Sales per Month (Integer) | 1 | 1 | 2 | Low | 1
R2-7 | Write SQL script to designate primary and foreign keys of new tables in the database | 2 | 3 | 4 | Medium | 3
Update Server and API Interfaces
R2-8 | Create endpoints in server to allow for modification of new database tables | 2 | 3 | 4 | Medium | 3
R2-9 | Create endpoints in user API interface that allow suppliers to post and remove products from marketplace | 2 | 3 | 4 | Medium | 3
R2-10 | Create GET endpoints in Medisail API interface to access customer and supplier statistics data | 2 | 3 | 4 | Medium | 3
R2-11 | Develop functionality for statistics charting in Medisail API interface | 2 | 3 | 4 | Medium | 3
R2-12 | Test endpoints in Postman | 1 | 1 | 2 | Low | 1
Update User Interfaces
Supplier User Interface
R2-13 | Develop UI components that allow suppliers to post new products to the marketplace | 4 | 6 | 7 | Medium | 6
R2-14 | Test user interface to ensure that components correctly map to API endpoints | 4 | 5 | 5 | Medium | 5
Medisail User Interface
R2-15 | Develop UI components that allow Medisail employees to view analytics data rendered from API endpoints connected to new database tables | 4 | 6 | 7 | Medium | 6
R2-16 | Test user interface to ensure that components correct map to API endpoints | 4 | 5 | 5 | Medium | 5
Documentation
R2-17 | Write documentation for integrated system | 4 | 6 | 7 | Medium | 6
Test Integrated System
Unit Testing
R2-18 | Write unit tests for new server functionality | 3 | 4 | 4 | Medium | 4
R2-19 | Write unit tests for new Medisail API interface endpoints | 2 | 3 | 4 | Medium | 3
R2-20 | Write unit tests for user API interface that ensure that customers don't have access to posting new products | 2 | 3 | 4 | Medium | 3
R2-21 | Write tests for customer user interface | 1 | 1 | 2 | Low | 1
R2-22 | Write tests for supplier user interface marketplace product posting rendering capabilities | 1 | 2 | 3 | Medium | 2
R2-23 | Write tests for Medisail user interface data analytics rendering capabilities | 1 | 1 | 2 | Low | 1
R2-24 | Write tests for marketplace interface to ensure that new product postings are correctly rendered | 1 | 2 | 3 | Medium | 2
R2-25 | Write tests for shopping cart interface | 1 | 2 | 3 | Medium | 2
R2-26 | Conduct back end unit tests | 2 | 3 | 4 | Medium | 3
R2-27 | Conduct user interface tests | 2 | 3 | 4 | Medium | 3
R2-28 | Communicate results of unit tests with development team | 1 | 2 | 3 | Medium | 2
R2-29 | Modify system based on test results (if needed) | 2 | 3 | 4 | Medium | 3
R2-30 | Retest user interfaces | 2 | 3 | 4 | Medium | 3
R2-31 | Reteset back end | 2 | 3 | 4 | Medium | 3
Integration Testing
R2-32 | Write integration tests between supplier user interface and server | 3 | 5 | 6 | Medium | 5
R2-33 | Write integration tests between Medisail user interface and server | 3 | 5 | 6 | Medium | 5
R2-34 | Write integration tests between marketplace user interface and server | 3 | 5 | 6 | Medium | 5
R2-35 | Write integration tests between user API interface and database | 2 | 4 | 5 | High | 5
R2-36 | Write integration tests between Medisail API interface and database | 3 | 5 | 7 | High | 7
R2-37 | Write mocked integration tests between user interfaces and database | 1 | 1 | 2 | Low | 1
R2-38 | Conduct integration tests between user interfaces and server | 1 | 2 | 3 | Medium | 2
R2-39 | Conduct integration tests between server and database | 1 | 2 | 3 | Medium | 2
R2-40 | Conduct integration tests between user interfaces and database | 1 | 2 | 3 | Medium | 2
R2-41 | Communicate results of integration tests with development team | 1 | 2 | 3 | Medium | 2
R2-42 | Modify system based on test results (if needed) | 2 | 4 | 5 | Medium | 4
R2-43 | Retest integration between user interface and server | 1 | 2 | 3 | Medium | 2
R2-44 | Retest integration between server and database | 1 | 2 | 3 | Medium | 2
R2-45 | Retest integration between user interface and database | 1 | 2 | 3 | Medium | 2
System Testing
R2-46 | Write system tests of the entire integrated system | 5 | 6 | 7 | High | 7
R2-47 | Conduct system tests of the integrated system | 7 | 7 | 8 | High | 8
R2-48 | Communicate results of system tests with development teams | 2 | 4 | 5 | Medium | 4
R2-49 | Modify system based on test results (if needed) | 5 | 6 | 7 | High | 7
R2-50 | Reconduct system tests | 2 | 4 | 5 | Medium | 4
Deploy Release 2
Conduct Required Trainings
R2-51 | Update sales manager on new capabilities of integrated e-procurement system | 2 | 3 | 4 | Low | 2
R2-52 | Train Medisail non-technical employees on integrated e-procurement system analytics capabilities | 2 | 3 | 4 | Medium | 3
Pre-Deployment Marketing
R2-53 | Create advertisement materials for integrated product | 2 | 3 | 4 | Low | 2
Product Deployment
R2-54 | Deploy integrated system | 5 | 6 | 7 | Medium | 6
R2-55 | Monitor system performance after deployment | 5 | 6 | 7 | Low | 5
Collect Supplier Feedback on Analytics Capabilities
R2-56 | Create Medisail non-technical employee survey about new analytics capabilities | 1 | 2 | 3 | Low | 1
R2-57 | Create new customer survey with refined prompts based on results of Release 1 survey | 1 | 2 | 3 | Low | 1
R2-58 | Send survey to Medisail non-technical employees who use the system | 1 | 2 | 3 | Low | 1
R2-59 | Send revised survey to customers | 1 | 2 | 3 | Low | 1
R2-60 | Collect and analyze feedback | 4 | 5 | 6 | Low | 4
R2-61 | Share survey feedback with team | 1 | 2 | 3 | Low | 1
Release 3: Advanced System
Adjust Plan Based on Supplier Feedback
R3-1 | Determine which aspects of feedback are relevant | 4 | 5 | 6 | Low | 4
R3-2 | Revise Release 3 requirements based on feedback assessment | 4 | 5 | 6 | Low | 4
Update Backend for Advanced Analytics
User API Interface
R3-3 | Write SQL queries to query analytics data from database for suppliers | 2 | 4 | 5 | Medium | 4
R3-4 | Write SQL queries to query analytics data from database for customers | 2 | 4 | 5 | Medium | 4
R3-5 | Create endpoints for analytics data for supplier UI | 1 | 3 | 4 | Medium | 3
R3-6 | Create endpoints for analytics data for user UI | 1 | 3 | 4 | Medium | 3
R3-7 | Test endpoints to ensure that supplier and user analytics data is mapped correctly | 1 | 2 | 3 | Medium | 2
Tableau Functionality
R3-8 | Negotiate and obtain Tableau license | 4 | 6 | 8 | High | 8
R3-9 | Review Tableau documentation | 3 | 4 | 5 | Medium | 4
R3-10 | Refine database tables as needed per Tableau documentation | 2 | 4 | 6 | High | 6
R3-11 | Create Tableau-specific API endpoints for suppliers | 1 | 3 | 4 | Medium | 3
R3-12 | Create Tableau-specific API endpoints for customers | 1 | 3 | 4 | Medium | 3
R3-13 | Create Tableau-specific API endpoints for Medisail non-technical employees | 1 | 3 | 4 | Medium | 3
R3-14 | Test all Tableau endpoints | 1 | 2 | 3 | Low | 1
Update Frontend for Advanced Analytics
R3-15 | Create UI components in customer user interface to render analytics data from database | 4 | 6 | 7 | High | 7
R3-16 | Create UI components in customer user interface to render Tableau graphics and charts | 4 | 5 | 7 | High | 7
R3-17 | Create UI components in supplier user interface to render analytics data from database | 4 | 6 | 7 | High | 7
R3-18 | Create UI components in supplier user interface to render Tableau graphics and charts | 4 | 6 | 7 | High | 7
R3-19 | Create UI components in Medisail user interface to render Tableau graphics and charts | 4 | 6 | 7 | High | 7
R3-20 | Test database analytics rendering in customer and supplier user interfaces | 2 | 3 | 5 | High | 5
R3-21 | Test Tableau integration in all user interfaces | 2 | 3 | 5 | High | 5
Documentation
R3-22 | Write documentation for advanced system | 3 | 4 | 5 | Medium | 4
Test Advanced System
Unit Testing
R3-23 | Write unit tests for data analytics API endpoints to ensure that only applicable data is accessible | 3 | 4 | 4 | Medium | 4
R3-24 | Write unit tests for Tableau API endpoints | 2 | 3 | 4 | Medium | 3
R3-25 | Write unit tests for new Medisail API interface endpoints to ensure that all data analytics is accessable | 2 | 3 | 4 | Medium | 3
R3-26 | Write tests for customer user interface data analytics capabilities | 1 | 1 | 2 | Low | 1
R3-27 | Write tests for supplier user interface data analytics capabilities | 1 | 2 | 3 | Medium | 2
R3-28 | Write tests for Medisail user interface data analytics rendering capabilities | 1 | 1 | 2 | Medium | 1
R3-29 | Write tests for Tableau integration in customer user interface | 1 | 2 | 3 | Medium | 2
R3-30 | Write tests for Tableau integration in supplier user interface | 1 | 2 | 3 | Medium | 2
R3-31 | Write tests for Tableau integration in Medisail user interface | 2 | 3 | 4 | Medium | 3
R3-32 | Conduct back end unit tests | 2 | 3 | 4 | Medium | 3
R3-33 | Conduct user interface tests | 1 | 2 | 3 | Medium | 2
R3-34 | Communicate results of unit tests with development team | 2 | 3 | 4 | Medium | 3
R3-35 | Modify system based on test results (if needed) | 2 | 3 | 4 | Medium | 3
R3-36 | Retest user interfaces | 2 | 3 | 4 | Medium | 3
R3-37 | Reteset back end | 2 | 3 | 4 | Medium | 3
Integration Testing
R3-38 | Write integration tests between supplier user interface and server | 1 | 2 | 3 | Medium | 2
R3-39 | Write integration tests between Medisail user interface and server | 1 | 2 | 3 | Medium | 2
R3-40 | Write integration tests between marketplace user interface and server | 1 | 2 | 3 | Medium | 2
R3-41 | Write integration tests between user API interface and database | 2 | 4 | 5 | High | 5
R3-42 | Write integration tests between Medisail API interface and database | 2 | 4 | 5 | High | 5
R3-43 | Write mocked integration tests between user interfaces and database | 3 | 5 | 7 | High | 7
R3-44 | Conduct integration tests between user interfaces and server | 1 | 2 | 2 | Medium | 2
R3-45 | Conduct integration tests between server and database | 1 | 2 | 3 | Medium | 2
R3-46 | Conduct integration tests between user interfaces and database | 1 | 2 | 3 | Medium | 2
R3-47 | Communicate results of integration tests with development team | 1 | 2 | 3 | Medium | 2
R3-48 | Modify system based on test results (if needed) | 1 | 2 | 3 | Medium | 2
R3-49 | Retest integration between user interface and server | 1 | 2 | 3 | Medium | 2
R3-50 | Retest integration between server and database | 1 | 2 | 3 | Medium | 2
R3-51 | Retest integration between user interface and database | 1 | 2 | 3 | Medium | 2
System Testing
R3-52 | Write system tests of the entire advanced system | 5 | 6 | 7 | High | 7
R3-53 | Conduct system tests of the advanced system | 7 | 7 | 8 | High | 8
R3-54 | Communicate results of system tests with development teams | 2 | 4 | 5 | Medium | 4
R3-55 | Modify system based on test results (if needed) | 5 | 6 | 7 | High | 7
R3-56 | Reconduct system tests | 2 | 4 | 5 | Medium | 4
Deploy Release 3
Conduct Required Trainings
R3-57 | Update sales manager on new capabilities of advanced e-procurement system | 1 | 2 | 3 | Low | 1
R3-58 | Train Medisail non-technical employees on new analytics capabilities | 3 | 6 | 7 | Medium | 6
R3-59 | Train customers on new analytics capabilities | 6 | 7 | 8 | Medium | 7
R3-60 | Train suppliers on new analytics capabilities | 6 | 7 | 8 | Medium | 7
Pre-Deployment Marketing
R3-61 | Create advertisement materials for advanced product | 1 | 2 | 3 | Low | 1
R3-62 | Conduct sales calls with potential new customers | 4 | 5 | 7 | High | 7
Product Deployment
R3-63 | Deploy advanced system | 3 | 5 | 9 | High | 9
R3-64 | Monitor system performance after deployment | 3 | 6 | 9 | High | 9
End of Project Activities
Product Adoption
EOP-1 | Plan product education workshops for customers and suppliers | 2 | 3 | 4 | Low | 2
EOP-2 | Schedule product education workshops | 1 | 1 | 1 | Low | 1
EOP-3 | Conduct product education workshops | 4 | 6 | 8 | Medium | 8
EOP-4 | Gather feedback from customers and suppliers during workshops | 2 | 3 | 4 | Low | 2
EOP-5 | Train Medisail sales teams and customer support on product | 4 | 6 | 8 | Medium | 6
Continuous Improvement
EOP-6 | Send monthly surveys to customers and suppliers | 1 | 1 | 2 | Low | 1
EOP-7 | Gather feedback from surveys | 1 | 2 | 3 | Low | 1
EOP-8 | Discuss results of surveys | 3 | 4 | 5 | Low | 3
EOP-9 | Determine feasibility of improvements suggested in survey results | 3 | 6 | 8 | Low | 3
EOP-10 | Implement accepted improvements to software system | 1 | 5 | 10 | Medium | 5

## Resources
Role | Role Description | Comments | Hourly Rate | Source | FTE/PTE
Project Manager (PM) | Responsible for organizing and planning the e-procurement software system project. Communicates with stakeholders and development team and defines project goals, MOV, and keeps project on track. |  | 68 | Salary.com | FTE
Senior Developer (SRD) | Leads and oversees development team and assists with all aspects of development. |  | 68 | Salary.com | FTE
Backend Developer (BED) | Responsible for developing the backend components of the application including the server and API interfaces. Responsible for integrating backend components with frontend componenets and backend components with the databases. |  | 58 | Salary.com | FTE
Frontend Developer (FED) | Responsible for developing the frontend components of the application including the customer UI, supplier UI, Medisail UI, and marketplace UI. Responsible for integrating frontend components with backend components. |  | 57 | Salary.com | FTE
Database Administrator (DBA) | Responsible for creating and maintaining the databases. |  | 34 | Salary.com | FTE
QA Tester (QAT) | Responsible for creating and implementing unit, integration, and system tests. Communicates with the IT Manager and Senior Developer about results of test cases. |  | 25 | Salary.com | FTE
IT Manager (ITM) | Oversees the development team and acts as a liason between the development team and the Project Manager. |  | 68 | Salary.com | FTE
Sales Manager (SM) | Responsible for overseeing introduction of e-procurement product to customers. Communicates with Project Manager about capabilities of the system and limitations at each deployment phase. |  | 63 | Salary.com | FTE
System Administrator | Responsible for managing, updating, and patching our infrastructure system. |  | 53 | Salary.com | FTE

## Scratch
We can delete this sheet when we submit. I am just keeping things I don't want to get lost here
Formula for team calc: =Resources!$D$3*I5 + Resources!$D$4*J5 + Resources!$D$5*K5 + Resources!$D$6*L5 + Resources!$D$7*M5 + Resources!$D$8*N5 + Resources!$D$9*O5